## Outstanding
West Yorkshire Police and Crime Panel Action Log |  |  |  |  | Item 11
Date | Item | Agreed Action | Attributed to | Date for completion | Action undertaken | Status
2015-02-06 | 5.1 | Precept commitment 1 Police officer recruitment reflects the diversity of West Yorkshire. The PCC provides an update to Panel on 6 Mar | PCC | 2015-06-12 | Update given on 6th March. KL to contact the Force re: recruitment intakes and provide information to PCP officers.
2015-02-06 | 5.1 | Precept commitment 2 Have clear longer-term workforce strategy in place on the shape and size of frontline policing in West Yorkshire. | PCC | 2015-09-11 | Update in private briefing session on 6 March. MBW to report back in Sep 2015.
2015-02-06 | 5.1 | Precept commitment 3 Have clear longer-term estates strategy in place which maxmises the value and use of land and property assets | PCC | 2015-09-11 | Update in private briefing session on 6 March. MBW to report back in Sep 2015.
2015-02-06 | 5.1 | Precept commitment 4 Improve the statistical validity of the Community Conversation survey involving Panel in the development of the 2015 survey. Include the council tax payer question. | PCP Officers / OPCC | TBC | ED to liase with CP at the OPCC.
2015-02-06 | 5.1 | Precept commitment 5 Increase ambition to maximise Home Office innovation funding to a level over and above the top-sliced contribution that West Yorkshire makes. | PCC | TBC | HO Innovation Fund report to Panel on 24 April 15.
2015-02-06 | 5.1 | Precept commitment 6 Ensure that a robust evaluation of the first year of transformation funding is undertaken which includes the development of an exit strategy as well as a more robust business case process. | PCC | TBC | KL to speak to Sophie re: date of report.
2014-11-07 | 5.7.2 | That the Commissioner provides information to the Panel on the status of the review of the Divisional Resourcing Model. | PCC | 2015-04-14 | PCC explained Ward Based Needs Assessment took place not a review of the Divisional Resourcing model. Information to be shared outside of the meeting cycle. Still awaiting comparative info. Requested from OPCC several times. KL to speak to MBW re: discussing this with AL at tje 1:1 on 14 April | X
2015-01-15 | 7.6 | Martin Goldman of the CPS to be invited to attend the Panel meeting when LCJB performance data is presented | LCJB | 2015-04-24 | Geoff Dodd has agreed to write the performance report. Geoff Dodd and / or Martin Goldman to attend. KL to confirm that Geoff Dodd is attending. | X
2014-11-07 | 6.4.1 | Victim Services – That the Commissioner brings a high-level evaluation report of the sixteen victim services projects in the new year. | PCC | 2015-04-24 | Report to Panel meeting on 24 April 2015. | X
2014-04-11 | 7.4.1 | That the Commissioner look further into this issue (use of police bail) and come back to the Panel within the next six months with an action plan addressing any necessary improvements. | PCC | 2015-04-24 | Report back to go to Panel meeting along with Acting Chief Constable in October. Report to the October meeting – Completed. Requested update in 6 months. To include WYP's response to the new bail measures time limit of 28 days. | X
2014-09-12 | 10.8.1 | That a report giving a progress update on all the individual recommendations from the DIP review are brought to a future meeting. | PCC | 2015-04-24 | Request for the DIP funding to be allocated based on population and crime stats. Take into account the address of the perpetrator which may be different from the district the crime was committed in and how funding is allocated to cover this. | x
2015-03-06 | 7.4.1 | Commissioner updates Panel on whether WY Police places callers on hold upon answering their call. | PCC | 2015-04-24 | Update under Matters Arising from the minutes
2015-03-06 | 12.5.1 | That the Commissioner provides information on the Force's use of RIPA to hack into phones | PCC | 2015-04-24 | KL to provide response to PCP officers prior to the next Panel meeting.
2015-03-06 | 12.5.2 | That the Commissioner provides information on the number of police officers who resigned whilst being subject to misconduct investigations | PCC | 2015-04-24 | KL to provide response to PCP officers prior to the next Panel meeting. Information provided to Panel outside the meeting. COMPLETED
2014-11-07 | 7.5.2 | That the Commissioner report back in due course on the governance review of the Force which is nearing completion | PCC | 2015-04-24 | OPCC to confirm. Panel had some information from Isabel on 15 Jan 15 the PCC's governance review but no detail on the Force's. KL to speak to the Force and update Panel. Unsure as to whether the Force has undertaken a separate governance review. The Force have not undertaken a separate governance review but simply aligned their meeting structure with the new meeting structure of the OPCC. COMPLETED
2015-01-15 | 1.4 | PCP Officers to work with the OPCC to look at potential venues for future Panel meetings with the possibility of the Chief Constable or District Commander attending with the PCC | PCP Officers/ OPCC | 2015-04-30 | PCP Officers to consider venues in Districts and liaise with KL before end April 15.
2014-04-11 | 8.10.2 | That the Commissioner considers how the Panel might provide help and support as he develops his plan to respond to points raised by the Crawford Review. | OPCC / PCP Officers | 2015-04-30 | Cllr Wassell has volunteered to work with the OPCC on the Crawford Review implementation plan. Julie Reid to contact the PCP Officers to arrange. Initial meeting has already taken place between Cllr Wassell, Julie Reid and PSD. KL to speak to JR re: Crawford Review implementation. PCP officers to work with the OPCC to develop new complaints process for Panel.
2014-11-07 | 8.5.1 | That the Commissioner invites Panel members to future Safer Communities funding aware events | PCC | 2015-08-01 | Awards were cancelled due to snow. Alternative dates to be supplied by KL. First date is in August 2015, venues yet to be confirmed.
2014-09-12 | 14.7.1 | That the Commissioner provides a report to the Panel within six months on the progress made against the recommendations highlighted within HMIC’s Crime Data Integrity report. | PCC | 2015-10-09 | Reported to 6th March. Further report to come back to Panel following HMIC re-inspection
2014-11-07 | 6.4.2 | Out of Court Disposal Pilot – that the Commissioner provides a report to the Panel on the pilot the new out of court disposals in West Yorkshire | PCC | 2016-03-01 | Deferred from 6 Mar 15 agenda by Chair of Panel. OPCC to provide a briefing of the scope of the pilot outside of the meeting. Formal report after pilot ends in Nov 15.
Press Alt key and enter to move down a line within a cell

## Completed
West Yorkshire Police and Crime Panel Action Log
Date | Item | Agreed Action | Attributed to | Date for completion | Action undertaken | Status
2014-11-07 | 7.5.1 | That the Commissioner provide panel with details of the terms of reference and scope of the governance review which is currently being undertaken | PCC | ASAP | COMPLETED | C
2014-12-12 | 6.3.4 | That the Panel writes to the Home Office re: Panel’s powers in the complaints process | PCP Officers | ASAP | COMPLETED | C
2014-12-12 | 6.3.5 | That the Panel writes to the PCC re: the complaints process to ensure that complainants are regularly updated | PCP Officers | 2014-12-19 | COMPLETED | C
2014-12-12 | 7.9.1 | That the Panel writes to the PCC re: the recommended appointment of Katherine Johnson to the Treasurer post | PCP Officers | 2014-12-19 | COMPLETED | C
2015-03-06 | 10.2 | PCP Officers to provide members with the latest version of published key decisions from the Commissioner's website | PCP officer | ASAP | COMPLETED
2015-01-15 | 1.5 | PCP Officers to email Members with Dave Livesey biog | PCP Officers | 2015-02-16 | COMPLETED
2015-01-15 | 3.3 | PCP Officers to draft key questions for Dave Livesey on the Government's response to the Home Affairs Select Committee report on PCCs | PCP Officers | 2015-02-26 | COMPLETED
2014-12-12 | 15.4.1 | That the PCC brings a report on 101 call handling to a future meeting and provides reasons to the Panel why WYP did not respond to the BBC’s FOI request | PCC | 2015-03-06 | COMPLETED
2014-11-07 | 12.5.1 | That the Joint Independent Audit Committee considers crime data integrity and the strategic workforce plan as part of their work programme. | Trevor Lake, Joint Audit Committee | Ongoing | This is being considered by AC. Removed from PCP action list. COMPLETED
2015-03-06 | 16.2.1 | That a complaints Sub- Committee meets to consider the appeal regarding the non-recording of a complaint | PCP Officer | 2015-03-18 | COMPLETED
2014-12-12 | 9.6.1 | That the PCC updates Panel on the progress of business cases | PCC | 2015-04-24 | Duplicate Action. Removed from Action Log.
2014-12-12 | 9.6.3 | Paul Whiteley to attend a future meeting of the Panel re: transformation fund projects | OPCC | 2015-04-24 | Duplicate Action. Removed from Action Log.
2014-12-12 | 9.6.2 | That the PCC ensures that Transformation Fund projects are reviewed and expected outcomes are monitored and measured | PCC | Ongoing | Duplicate Action. Removed from Action Log.
2014-12-12 | 8.7.1 | That the PCC shares the Estates Strategy with the Panel | PCC | 2015-10-09 | Duplicate Action. Removed from Action Log.
2014-11-07 | 5.7.1 | That the Commissioner brings a report on the strategic workforce plan to a future meeting of the Panel. | PCC | 2015-10-09 | Duplicate Action. Removed from Action Log.
Completed
Ongoing requires review
Requires attention
Press Alt key and enter to move down a line within a cell