## Outstanding
West Yorkshire Police and Crime Panel Agreed Action Log | [7 empty] | ITEM 11
No. | Date | Item | Agreed Action | Attributed to | Date for completion | Action undertaken | Action undertaken | Status
1 | 2025-02-07 |  | Precept Commitment 1: That the Mayor works with West Yorkshire Police to retain and increase the numbers of PCSO’s where funding allows | Mayor | Regular updates
2 | 2025-02-07 |  | Precept Commitment 2: Provide the Panel with a report back on Priority Based Budgeting to assure them that required efficiencies are on track in line with projections to meet future funding shortfalls and set out contingincy plans should the efficiences not be realised | Mayor | 2025-12-01
3 | 2025-02-07 |  | Precept Commitment 3: To report back mid-year on the reserves position providing assurances that these are kept at a sustainable level and reduce the reliance on reserves going forward | Mayor | 2025-12-01
4 | 2025-02-07 |  | Precept Commitment 4: Initiate the 2026/27 budget consultation early, providing an extended timeframe and continuing to aim for wider engagement from all community sectors | Mayor | 2025-12-01
5 | 2023-12-08 | 5.6.1 | The Deputy Mayor to share an upcoming evaluation of the CARA programme, including baseline data and success criteria calculations. | DMPC | 2026-03-01 | Paper to come to panel in March 2026 |  | Ongoing
6 | 2024-04-12 | 6.8.1 | Following recruitment, and establishment in role, the Chair of the joint panel on ethics to be invited to a future Panel meeting. | SW / Mayor's Office | 2025-01-01 | Ethics panel chair is Hilary Barber. |  | Ongoing
7 | 2024-04-12 | 5.9.1 | The Deputy Mayor to work with WYP to look at the possibility of correlating an increase in the volume of traffic with the numbers of people killed or seriously injured on the roads. | DMPC | 2025-04-01 | This was included in the panel paper in July - point 2.13 The policy manager talked at panel about the DfT using vehicle miles as an indicator as volume is not something that is used. |  | Complete
8 | 2025-04-11 | 5.10.1 | An interim report to be brought to Panel in six months’ time on progress towards the Force’s IDM targets. | DMPC | 2025-11-01 | Brought forward to December meeting |  | Ongoing
11 | 2025-07-11 | 6.12.1 | The Deputy Mayor to include data and narrative specific to the M62 in future Vision Zero and performance reports. | DMPC | 2025-09-01 | Noted for the next Vision Zero report and was included in the September Performance report - extract below Additionally, the Camera Enforcement Unit works closely with National Highways and uses a range of camera technology to enforce speed limits and ‘Red X’ lane infringements on the motorway network. There is long term enforcement activity on the managed motorway sections of the M1 and M62 and a total of 6405 offences have been detected following camera activations during the last quarter. |  | Complete
12 | 2025-09-11 | 5.9.1 | The Deputy Mayor to look at producing a shorter, summary document to be read alongside the Annual Report, including a glossary of terms. | DMPC | 2026-02-01 | Shorter document ongoing - glossary included in the annual report. |  | Ongoing
13 | 2025-09-11 | 5.9.2 | The Deputy Mayor to circulate links to reports from the West Yorkshire Violence Reduction Partnership and the Department for Education which address the link between school exclusions and criminality. | DMPC | 2025-11-01 | The VRP works closely with the Youth Endowment Fund and their most recent research is found at https://youthendowmentfund.org.uk/secondary-data-analysis/an-examination-of-the-association-between-school-absence-exclusion-and-violent-crime/ The VRP did do a piece of research in 2023 - https://www.westyorks-ca.gov.uk/media/10866/neet-young-people-not-in-education-employment-or-training-and-violent-crime.pdf |  | Complete
14 | 2025-09-11 | 5.9.3 | The Deputy Mayor’s office to further investigate the possibility of collating figures to show the impact of Naloxone in avoiding deaths caused by overdoses. | DMPC | 2026-03-01 | Raised with the policy lead at WYCA and being actioned. |  | Ongoing
15 | 2025-09-11 | 6.8.1 | The Deputy Mayor to write to local authorities to raise the issue of anti-social firework use and ask what criteria is used to grant licences for events. | DMPC | 2026-02-01 | Raised with the partnerships lead at WYCA and being actioned. |  | Ongoing

## Completed
West Yorkshire Police and Crime Panel Action Log
Date | Item | Agreed Action | Attributed to | Date for completion | Action undertaken | Status
2014-11-07 | 7.5.1 | That the Commissioner provide panel with details of the terms of reference and scope of the governance review which is currently being undertaken | PCC | ASAP | COMPLETED | C
2014-12-12 | 6.3.4 | That the Panel writes to the Home Office re: Panel’s powers in the complaints process | PCP Officers | ASAP | COMPLETED | C
2014-12-12 | 6.3.5 | That the Panel writes to the PCC re: the complaints process to ensure that complainants are regularly updated | PCP Officers | 2014-12-19 | COMPLETED | C
2014-12-12 | 7.9.1 | That the Panel writes to the PCC re: the recommended appointment of Katherine Johnson to the Treasurer post | PCP Officers | 2014-12-19 | COMPLETED | C
2015-03-06 | 10.2 | PCP Officers to provide members with the latest version of published key decisions from the Commissioner's website | PCP officer | ASAP | COMPLETED
2015-01-15 | 1.5 | PCP Officers to email Members with Dave Livesey biog | PCP Officers | 2015-02-16 | COMPLETED
2015-01-15 | 3.3 | PCP Officers to draft key questions for Dave Livesey on the Government's response to the Home Affairs Select Committee report on PCCs | PCP Officers | 2015-02-26 | COMPLETED
2014-12-12 | 15.4.1 | That the PCC brings a report on 101 call handling to a future meeting and provides reasons to the Panel why WYP did not respond to the BBC’s FOI request | PCC | 2015-03-06 | COMPLETED
2014-11-07 | 12.5.1 | That the Joint Independent Audit Committee considers crime data integrity and the strategic workforce plan as part of their work programme. | Trevor Lake, Joint Audit Committee | Ongoing | This is being considered by AC. Removed from PCP action list. COMPLETED
2015-03-06 | 16.2.1 | That a complaints Sub- Committee meets to consider the appeal regarding the non-recording of a complaint | PCP Officer | 2015-03-18 | COMPLETED
2014-12-12 | 9.6.1 | That the PCC updates Panel on the progress of business cases | PCC | 2015-04-24 | Duplicate Action. Removed from Action Log.
2014-12-12 | 9.6.3 | Paul Whiteley to attend a future meeting of the Panel re: transformation fund projects | OPCC | 2015-04-24 | Duplicate Action. Removed from Action Log.
2014-12-12 | 9.6.2 | That the PCC ensures that Transformation Fund projects are reviewed and expected outcomes are monitored and measured | PCC | Ongoing | Duplicate Action. Removed from Action Log.
2014-12-12 | 8.7.1 | That the PCC shares the Estates Strategy with the Panel | PCC | 2015-10-09 | Duplicate Action. Removed from Action Log.
2014-11-07 | 5.7.1 | That the Commissioner brings a report on the strategic workforce plan to a future meeting of the Panel. | PCC | 2015-10-09 | Duplicate Action. Removed from Action Log.
2014-11-07 | 5.7.2 | That the Commissioner provides information to the Panel on the status of the review of the Divisional Resourcing Model. | PCC | 2015-04-14 | PCC explained Ward Based Needs Assessment took place not a review of the Divisional Resourcing model. Information to be shared outside of the meeting cycle. Still awaiting comparative info. Requested from OPCC several times. KL to speak to MBW re: discussing this with AL at tje 1:1 on 14 April. MBW reluctant to share figures as political. Description of method sent to Members on 17 April 2015. COMPLETED
2015-01-15 | 7.6 | Martin Goldman of the CPS to be invited to attend the Panel meeting when LCJB performance data is presented | LCJB | 2015-04-24 | Geoff Dodd has agreed to write the performance report. Geoff Dodd and / or Martin Goldman to attend. KL to confirm that Geoff Dodd is attending. Geoff Dodd attended. COMPLETED
2014-09-12 | 10.8.1 | That a report giving a progress update on all the individual recommendations from the DIP review are brought to a future meeting. | PCC | 2015-04-24 | Request for the DIP funding to be allocated based on population and crime stats. Take into account the address of the perpetrator which may be different from the district the crime was committed in and how funding is allocated to cover this. COMPLETED
2015-03-06 | 7.4.1 | Commissioner updates Panel on whether WY Police places callers on hold upon answering their call. | PCC | 2015-04-24 | Update under Matters Arising from the minutes COMPLETED
2015-03-06 | 12.5.1 | That the Commissioner provides information on the Force's use of RIPA to hack into phones | PCC | 2015-04-24 | KL to provide response to PCP officers prior to the next Panel meeting.
2015-03-06 | 12.5.2 | That the Commissioner provides information on the number of police officers who resigned whilst being subject to misconduct investigations | PCC | 2015-04-24 | KL to provide response to PCP officers prior to the next Panel meeting. COMPLETED
2014-11-07 | 7.5.2 | That the Commissioner report back in due course on the governance review of the Force which is nearing completion | PCC | 2015-04-24 | OPCC to confirm. Panel had some information from Isabel on 15 Jan 15 the PCC's governance review but no detail on the Force's. KL to speak to the Force and update Panel. Unsure as to whether the Force has undertaken a separate governance review. KL stated that the Force has not undertaken a separate review. COMPLETED
2015-04-24 | 15.2.1 | PCP Officers to work with the OPCC with a view to changing the date of the July meeting | PCP Officers | 2015-05-08 | ED confirmed PCC availability on 10 July. Currently checking availability of Panel Members. Meeting remains as 17 July due to diary commitments. COMPLETED
2015-04-24 | 16.1 | Cllr Lowe stated that she would write to Cllr Les Carter on behalf of the Panel to thank him for his hard work and commitment over the years and to wish him well in his retirement. | PCP Officers / Cllr Lowe | 2015-05-15 | COMPLETED
2015-04-24 | 9.8.1 | That the OPCC circulate the missing CJS performance appendix outside of the meeting | OPCC / PCP Officers | ASAP | COMPLETED
2014-11-07 | 6.4.1 | Victim Services – That the Commissioner brings a high-level evaluation report of the sixteen victim services projects in the new year. | PCC | 2015-06-12 | Report to Panel meeting on 24 April 2015. DEFERRED to 12 June 2015
2015-04-24 | 13.4.1 | That due to the poor response from Crime and Disorder Scrutiny Committees, Panel Members were asked to encourage participation from their respective authorities. | PCP Members | Ongoing | PCP Officers have sent out the latest Local Perspectives Survey and Members have been asked for their assistance in ensuring it is completed on time. Will report to the July Panel meeting.
2015-04-24 | 13.4.2 | Police and Crime Panel Officers to ensure Panel Members are aware when the Local Perspectives information is requested from their respective authorities. | PCP Officers | Ongoing | PCP Officers have sent out the latest Local Perspectives Survey and Members have been asked for their assistance in ensuring it is completed on time. Will report to the July Panel meeting.
2015-04-24 | 8.5.1 | That the Commissioner provides a report on the work of the WyFi team to a future meeting | PCC | 2015-07-17 | Included on agenda
2015-06-12 | 9.2.2 | That the Annual Report be sent to all elected Members across West Yorkshire as well as the Policing Minister, Keith Vaz (Home Affairs Select Committee), David Livesey (Home Office) and Mike Cunningham (HMIC). | PCP Officers | ASAP | COMPLETED
2015-01-15 | 1.4 | PCP Officers to work with the OPCC to look at potential venues for future Panel meetings with the possibility of the Chief Constable or District Commander attending with the PCC | PCP Officers/ OPCC | 2015-04-30 | PCP Officers to consider venues in Districts and liaise with KL before end April 15. KL to check MBW's diary for the September meeting. Venue confirmed as Dewsbury Town Hall. COMPLETED.
2014-04-11 | 8.10.2 | That the Commissioner considers how the Panel might provide help and support as he develops his plan to respond to points raised by the Crawford Review. | OPCC / PCP Officers | 2015-04-30 | Cllr Wassell has volunteered to work with the OPCC on the Crawford Review implementation plan. Julie Reid to contact the PCP Officers to arrange. Initial meeting has already taken place between Cllr Wassell, Julie Reid and PSD. KL to speak to JR re: Crawford Review implementation. PCP officers to work with the OPCC to develop new complaints process for Panel. Update paper on the Crawford review implementation to go to the June meeting.
2015-06-12 | 12.3.1 | PCP Officers to invite an LGA representative to the Panel’s Awayday | PCP Officers | 2015-06-25 | LGA rep has agreed to attend Panel Awayday 3 July 15. COMPLETED.
2015-06-12 | 17.6.3 | The Commissioner to circulate the letter regarding the Home Office Review of Police Targets and for the Panel to forward any views back to the OPCC | PCC | 2015-06-12 | Received from the OPCC on 12 June and sent out to Panel Members for their comments. JS asked that the OPCC provides the Panel with theirs and the Force response. OPCC to confirm with the PCC. OPCC response circulated to Members 8 July 15
2015-06-12 | 18.6.1 | That the Commissioner provides information to the Police and Crime Panel Officers on the reasons for the increase in blackmail | PCC | 2015-07-17
2014-11-07 | 8.5.1 | That the Commissioner invites Panel members to future Safer Communities funding award events | PCC | 2015-08-01 | Awards were cancelled due to snow. Alternative dates to be supplied by KL. First date is in August 2015, venues yet to be confirmed. First awards to be held on 6 August in Kirklees/Calderdale tbc. Members invited.
2015-07-17 | 13.3.2 | That the T/CC be invited to the Nov meeting to give an update on the SPR | PCC | 2015-07-29 | OPCC to invite T/CC Collins to Nov meeting | Completed
2015-07-17 | 5.9.3 | That the Commissioner circulate to the Panel for comment his proposed section on holding the Commissioner to account, as a matter of urgency | PCC | 2015-08-15 | Members should be allowed time to comment before publication of the Annual Report. Circulated to Members and response provided on 21 August 15. | Completed
2015-07-17 | 5.9.2 | That the Commissioner fully review the grammar and writing of the Annual Report before publication | PCC | 2015-08-31 |  | Completed
2015-07-17 | 5.9.4 | The Commissioner to review the data in the annual report to ensure it is as up to date as possible | PCC | 2015-08-31 |  | Completed
2015-07-17 | 8.8.3 | The Commissioner to forward his response to the HMIC inspection report on Child Protection | PCC | 2015-08-31 | Received from OPCC on 21 July and forwarded to Panel Members | Completed
2015-06-12 | 17.6.1 | The Commissioner to ask the Temporary Chief Constable to update Chief Officer Profiles on the Force website. | PCC | Ongoing | The website has been updated. | Completed
2015-07-17 | 8.8.2 | The Commissioner to forward information to the Panel on HMIC reporting on efficiency and effectiveness and to arrange discussion at a future meeting | PCC |  | Letter received by OPCC from HMIC about Force Management Statements and shared with Panel members July 2015. The changes aren’t due to be brought in until 2017 but happy to keep the Panel updated outside of meetings if any developments. | Completed
2015-07-17 | 6.3.1 | That the Commissioner provide further information regarding the staffing and work of the WyFi team in a much more user-friendly manner | PCC | 2015-08-31 | To be circulated prior to the meeting in Sept 15
2015-07-06 | 1:1 with AL and MBW | Commissioner has asked the Panel to consider reducing public meetings from 8 to 6, plus 2 additional private themed meetings | Panel Members | 2015-07-17 | Discussion at Panel meeting on 17 July. Decision made to maintain at 8. Dates for 2016 to be confirmed at meeting on 11 Sep 15.
2015-09-11 | 9.3.1 | Panel Officers to develop an outline of the scrutiny review of the Force’s treatment of vulnerable victims and vulnerable perpetrators. | PCP / OPCC | 2015-10-31 | To be discussed at Panel's private meeting on 9th Oct. ED to draft outline for OPCC to comment on prior to 9 Oct. Sent to OPCC on 21 Oct to finalise. | Completed
2015-04-24 | 14.2.1 | That Councillor Wassell (Wakefield), Councillor Scott (Kirklees), Councillor Walls (Bradford) and Councillor Barker (Wakefield) form a Complaints Sub Committee to specifically consider the complaint | PCP | 2015-10-31 | Await outcome from IPCC before proceeding. ED to advise. Appeal still with IPCC. ED contacted IPCC for a second time on 3 July. Awaiting response. IPCC have now referred complaint back to Panel 23 July 15. Complaints Sub Committee met on 21 August. Further information to be requested from the Commissioner prior to Complaints Sub Committee reconvening to discuss LR. | Completed
2015-09-11 | 6.9.1 | The Commissioner to provide information on the ANPR Transformation Project and the projected completion dates for installing ANPR cameras | PCC | 2015-11-13 | Requested by Cllr G Carter. Will also form part of the Transformation Update on 13 Nov 15. Panel members invited to ANPR Unit. | Completed
2015-09-11 | 11.4.1 | Panel Officers to circulate 2016 Panel meeting dates when confirmed | PCP | 2015-11-13 | Dates circulated. ED to confirm with PCP re: November date being changed at the meeting on 9th Oct | Completed
2015-09-11 | 12.7.2 | The Commissioner to provide the Force’s guidelines to staff on the use of social media | PCC | 2015-11-13 | Outside the formal meeting | Completed
2015-09-11 | 7 | The Commissioner to provide details of the number of BME officers by rank | PCC | 2015-11-13 |  | Completed
2015-06-12 | 9.2.3 | PCP to seek opportunities to launch the Annual Report to the media | PCP Officers | 2015-11-13 | ED to discuss with Cllrs Ahmed and Martin. | Completed
2015-09-11 | 13.4.1 | That the full Panel consider the appeal at its meeting on 13th November 15 | PCP | 2015-11-13 |  | Completed
2015-06-12 | 14.8.1 | The Commissioner to ensure that the Complaints Oversight (formely Crawford Review) implementation plan includes more detail and have clear timescales for each action | PCC | 2015-11-13 | The OPCC to incorporate the Panel's comments of the 12 June 15 and to report back to Nov or Dec meeting. | Completed
2015-09-11 | 8.8.1 | The Commissioner to provide a report on victims' hubs to a future meeting | PCC | 2015-11-13 | Verbal update provided on 13 Nov 15 | Completed
2015-11-13 | 14.2.1 | Make amendments to the Emergency Meetings Protocol as per the discussion | PCP | 2015-11-30 | PCP Officers to amend.
2015-07-17 | 13.3.1 | That the September meeting have a Prevent theme. Interested parties to be invited | PCP | 2015-12-11 | PCP Officers to discuss with OPCC. Prevent to be discussed at Dec 15 meeting (part of SPR report).
2015-11-13 | 8.3.1 | The Commissioner invited Members to visit one of the Victims' Hubs | PCP | 2016-03-31 | PCP Officer to provide details to Members.
2015-04-24 | 6.5.1 | That the Commissioner continues to look at opportunities for joint commissioning where possible | PCC | Ongoing | KL to speak to Trish Holder for an update (24/9/15). Currently awaiting the CSR annoucement to finalise future plans and look at joint commissioing opportunities. Partner Transformation Event being held by the PCC early December. Invite has been sent to Chair of the PCP.
2015-09-11 | 6.9.2 | The Commissioner agreed to include homicide figures in the next quarterly performance report | PCC | 2015-12-11 | Requested by Roger Grasby.
2015-11-13 | 13.3.1 | A new Complaints Sub Panel to be formed to consider new complaints | PCP | 2016-01-14 | Meeting arranged for 9 December. Information requested from complainant and PCC. 2nd meeting arranged in Jan 16.
2015-09-11 | 12.7.1 | The Commissioner to provide further information on West Yorkshire Police’s approach to the seizure and sale of cars | PCC | 2015-12-11 | Outside the formal meeting. Information to be provided ahead of the meeting. KL has spoken to the Force. Aiming to provide it before December meeting.
2015-11-13 | 10.2.1 | The Commissioner was asked to provide full Panel with information on the full costs to West Yorkshire of the redeployment of Mark Gilmore. | PCC | 2015-12-11 | Update to be provided at the Dec meeting.
2015-09-11 | 7.8.1 | The Commissioner to provide a briefing to Members on the Strategic Workforce Plan, potentially at their private meeting on 9 October 2015 | PCC | 2016-01-22 | Agreed at 1:1 on 2 Dec 15 that this would be provided to the private meeting of the Panel in January.
2015-11-13 | 12.4.1 | Panel to consider the full PEEL report at a future meeting | PCC | 2016-03-11 | When all PEEL inspection reports are available.
2015-11-13 | 9.3.2 | That the Commissioner provides updates and involves Panel members in discussions about changes to overseeing the Police Complaints system. | PCC/PCP | Ongoing
2015-12-11 | 5.6.1 | That the Panel share details of Force recruitment with community groups to encourage applicants from diverse backgrounds | PCP
2015-06-12 | 17.6.2 | The Commissioner to keep the Panel informed of any progress on the Armed Forces Covenant | PCC | Ongoing | Dialogue is ongoing between the OPCC and WYP (04/11)
2015-09-11 | 5.9.2 | The Commissioner to provide details of police officers on restricted duties and how they are being utilised across the Force | PCC | 2016-03-11 | Requested by Roger Grasby. Information provided outside of formal meeting structure. More detailed report required for public meeting (13 Nov 15)
2015-07-17 | 8.8.1 | The Commissioner to look at the progression of co-location with the Fire and Rescue Service at Weetwood Police Station and respond to the Panel outside the meeting process | PCC | 2015-12-11 | Information to be provided ahead of the meeting on 11 Sep 15. Brief update provided on 11 Sep. Ongoing issue. Changes have been made to the original proposal from Leeds CC and WYFRS and alternative options are being explored by both (26/02)
2016-02-06 | 7.2 | Cllr G Carter to attend the LGA's Panel conference on 14 March with Sam | Panel | 2016-03-14 | SW / ED to try and secure more places for Cllr Ahmed and Mrs Sykes to attend. Places secured for 4 people to attend. SW / ED to arrange train tickets for Members.
2016-03-11 | 7.5.1 | OPCC to re-issue the performance report appendices due to an error being highlighted | PCC | 2016-03-31 | ED emailed LW on 31 March for the amended report. Sent to members 31/3/16
2016-03-11 | 13.3.2 | That an additional meeting of the full Police and Crime Panel be convened on 6 April to consider a complaint appeal | Panel | 2016-04-06
2016-03-11 | 12.2.1 | That the reference to senior staff in part 7 of the Panel's Arrangements and Rules of Conduct be removed and replaced with Deputy PCC | Panel | 2016-03-31
2016-03-11 | 13.3.1 | A new Complaints Sub Panel to be arranged to consider the newly recorded complaint. | Panel | 2016-04-30 | Meeting arranged on 26 April 16
2016-03-11 | 11.5.1 | The PCC to share his response to HMIC's report on Child Protection Post-Inspection Review report | PCC | 2016-04-22
2016-04-22 | 9.2.1 | That the PCC shares his response to HMIC's report on WYP's Child Protection Inspection | PCC | 2016-04-22 | Emailed to Panel Members on 22 April 16.
2016-04-22 | 10.12.1 | That arrangements are made for Mr Lake to meet with the Scrutiny Review Team to discuss commissioning of services. | PCP | 2016-06-10 | ED/SW to contract Trevor Lake to arrange.
2015-11-13 | 2.4.3 | The Commissioner agreed to look at the College of Policing's Equality and Diversity initiative and see what learning there might be for West Yorkshire. | PCC | 2016-01-31 | Clarity on the specific initiative is required and email sent to SW/ED to liaise with JS (17/02)
2016-06-10 | 9.1.1 | Complaints Procedures - officers to make final amendments | PCP | 2016-07-15
2016-06-10 | 17.1.5 | The Commissioner provides detail on the number of successful BME applicants overall and female BME applicants to police officers | PCC | 2016-07-15 | To be included in the recruitment report.
2016-06-10 | 17.4.3 | The Commissioner to provide the response from WYP on the IPCC report into Sussex | PCC | 2016-07-15 | Kelly requested from WYP - awaiting response.
2016-06-10 | 18.1.3 | Panel to write to Mike Penning MP in support of the proposal to change the names of PCPs to include Fire where appropriate | PCP | 2016-06-17 | Letter sent on 14 June 16
2016-06-10 | 19.4 | Inform the complainant of the outcome of the review of the Complaints Sub Panel's decision | PCP | 2016-06-17 | Letter sent on 14 June 16
2016-07-15 | 15.1 | Panel officers to draft a response to PCC's partnership consultation survey and circulate to members for approval prior to submission | Panel | 2016-08-01
2016-07-15 | 5.7.3 | ACC Battle to check whether data on arrests that were directly attributable to ANPR is available prior to the introduction of the enhanced ANPR system | PCC | 2016-09-09 | There were 51 arrests attributable to ANPR in the previous year and this will be used as a baseline to measure the effectiveness of the enhanced ANPR system.
2016-07-15 | 6.5.1 | The PCC to provide detail of how he is holding the Force to account for the 5/6% 'real' increase in recorded crime | PCC | 2016-09-09 | To be included in the Quarterly Performance report.
2016-07-15 | 11.2.1 | Cllrs Lowe, Wassell and Wilkinson to form a sub panel to recruit independent members | PCP | 2016-11-04 | Outline timetable to be brought forward by one week. Shortlisting - 10am on 26 Sep 16 Interviews - 1pm on 6 Oct 16 Panel officers to arrange rooms. Rooms arranged.
2016-09-09 | 14.4 | That Panel Members contact Panel Officers if they wish to attend the Panel Conference on 20 October 16 | PCP |  | Alan, Josie and Sam to attend
2016-09-09 | 14.3 | That the Panel's Annual Report be disseminated widely | PCP |  | Panel officers to distribute asap
2016-09-09 | 5.11.1 | Panel to provide a report to the PCC following the Interim Chief Executive confirmation hearing | PCP | 2016-10-14 | Panel Officers sent the report to the PCC on 12 Oct 16 and published it on the Panel's website
2016-10-07 | 6.7.1 | That Members provide feedback to Officers on the draft Police and Crime Plan | PCP | 2016-10-14 | Roger and Steve to meet with the OPCC on 19 October to discuss. Feedback provided to the OPCC. Panel to receive a revised Plan by 26 Oct 16.
2016-10-07 | 6.7.3 | Revised draft Police and Crime Plan to Panel before 4 November meeting | PCC | 2016-11-04 | Deadline 26 Oct 16
2016-10-07 | 6.7.4 | PCC to provide the Needs Assessment surrounding the Police and Crime Plan | PCC | 2016-11-04 | Deadline 26 Oct 16
2016-10-07 | 7.4.2 | Panel's Monitoring Officer to consider formalising the appointment of the 2 co-opted independent members | PCP | 2016-11-30 | Sam to discuss with Bernadette.
|  | That the PCC keeps the Panel informed re: recruitment of new Chief Constable | PCC | 2016-11-11 | Recruitment timetable sent to Panel Officers. Confirmation hearing to be held on 11 Nov 16.
2016-09-09 | 12b.5 | Panel to provide a report to the PCC following the Interim Chief Executive confirmation hearing | PCP | 2016-10-14 | Panel Officers sent the report to the PCC on 12 Oct 16 and published it on the Panel's website
2016-09-09 | 5.11.1 | That Members provide feedback to Officers on the draft Police and Crime Plan | PCP | 2016-10-14 | Roger and Steve to meet with the OPCC on 19 October to discuss. Feedback provided to the OPCC. Panel to receive a revised Plan by 26 Oct 16.
2016-10-07 | 6.7.1 | Revised draft Police and Crime Plan to Panel before 4 November meeting | PCC | 2016-11-04 | Deadline 26 Oct 16
2016-10-07 | 6.7.3 | PCC to provide the Needs Assessment surrounding the Police and Crime Plan | PCC | 2016-11-04 | Deadline 26 Oct 16
2016-10-07 | 6.7.4 | Panel's Monitoring Officer to consider formalising the appointment of the 2 co-opted independent members | PCP | 2016-11-30 | Sam to discuss with Bernadette.
2014-11-07 | 7.4.1 | That the Commissioner look further into this issue (use of police bail) and come back to the Panel within the next six months with an action plan addressing any necessary improvements. | PCC | 2017-12-15 | Report back to go to Panel meeting along with Temporary Chief Constable in October. Report to the October meeting – Completed. Requested update in 6 months. To include WYP's response to the new bail measures time limit of 28 days. Six month update required. Further six month update required in April 16. Particular reference to improvements in gathering technical and medical evidence. Further 6 month update required following Bail Act
2016-04-22 | 1.5.3 | The Commissioner to provide a report to a future Panel meeting on what actions WYP will be taking around disciplinary hearings for senior police officers in public. | PCC | 2016-11-04 | Panel wants to know the process
2016-07-15 | 5.7.1 | That the Panel be provided with a breakdown of police officer applicants by age | PCC | 2016-11-04
2016-09-09 | 5.7.2 | That the Panel be provided with information re: police officers on restricted / recuperative duties over time. | PCC | 2016-11-04
2016-09-09 | 6.8 | The Panel provides the PCC with information on where data sharing had been a problem amongst partners | PCP | 2016-11-04 | Cllr Hussain has provided clarification to the OPCC who have raised with WYP. Rob to update in due course (20 Oct 16).
2016-11-04 | 5.8.2 | Panel to produce a formal report with detailed recommendations following review of draft Plan | PCP Secretariat | 2016-11-08 | Report with recommendations sent to PCC and published. Response from PCC received and published
2016-11-04 | 6.8.2 | PCC to bring a more detailed report to the next meeting providing a comprehensive update on actions taken and next steps in implementing HMIC recommendations, also to include how the PCC is holding the CC to account and monitoring improvements | PCC | 2016-12-16
2016-03-11 | 12.1.1 | Officers to work together to propose a final version of the Memorandum of Understanding | PCP/PCC | 2016-09-09 | Panel Officers to draft MoU and liaise with OPCC. Sam liaising with Trish and Bernadette (13 Oct 16)
2016-09-09 | 7.4 | PCC's Commissioning Group to consider the Panel's Scrutiny Review of Commissioned Services | PCC | Ongoing PCC to report back in March 17 | Jo Sykes attended the Commissioning Group meeting and outlined the review. The Deputy Treasurer agreed to consider the recommendations. Jo Sykes to feedback to the Panel. Commissioner to report back to Panel in 6 months. PCC reported back to Panel in March 2017. Further update to come back to Panel in 6 months
2016-11-04 | 6.8.1 | PCC to keep Panel informed of any developments around the 17/18 provisional settlement | PCC | 2016-12-31
2016-12-16 | 5.92 | The Commissioner to give further consideration to covering more of the performance issues in his Annual Report | PCC | 2017-01-01
2016-12-16 | 5.9.3 | Clarify legal requirements in relation to the timeframes required for publishing an annual report | Wakefield Legal | 2017-01-01
2016-12-16 | 6.8.1 | That the Commissioner ensures future Performance reports include more detail about how he is holding the Force to account for performance | PCC | 2017-03-01
2016-12-16 | 8.2.1 | That 101 Call Handling be considered at the March meeting | PCC | 2017-03-01
2016-12-16 | 12.5.2 | Update on PO's on recuperative duties including comparative data from other forces | PCC | TBA | Comparative data not available from other Forces - will raise under matters arising
2016-11-04 | 10.4 | PCC to bring a report to the Panel on what actions he is taking to mitigate any safeguarding risks as a result of the de-regulation of taxi licensing | PCC | 2017-05-01
2016-12-16 | 6.8.2 | Commissiner to bring a report to Panel on the work of the Tri-Service Collaboration Board | PCC | 2017-05-01
2016-12-16 | 11.6.1 | Report to future panel on move from NOMs to CRC's | PCC | 2017-05-01
2016-12-16 | 11.6.2 | Commissioner to report on the Re-offending Stragegy in due course | PCC | 2017-05-01
2017-03-10 | 5.19.1 | Panel to feed any further comments in on the new format for Delivery Quarterly reporting | Panel | 2017-05-01
2017-03-10 | 11.6.1 | That the Force be congratulated on their achievement of a 'Good' rating for the HMIC Effectiveness inspection
2016-10-07 | 7.4.2 | PCC to try to ensure that the Priority Plans to support the Police & Crime Plan are completed by the end of December | PCC | 2016-12-31 | Draft Plans going to WY CSP forum end of Jan
2016-11-04 | 5.8.3 | PCC keep Panel updated on the latest position regarding the Funding Formula review and consults with Panel when proposals are available | PCC | 2016-03-10 | PCC to consult with Panel when proposals are available for consultation - expected around Mar 17
2016-11-04 | 11.6.2 | PCC to ensure that papers include the author and contact details and are sent to the PCP on time | PCC | ongoing
2017-03-10 | 9.4.1 | That the Commissioner keeps Panel updated on implementation of the new complaints legislation and brings an update on force complaints to a future Panel meeting | PCC | TBA
2017-05-05 | 5.8.1 | Susan Field to ask the CRC to provide more detail on the re-offending figures for West Yorkshire | PCC | end May | Further detail circulated
2017-05-05 | 7.5.1 | That the Commissioner be thanked for his involvememt and work with partners on taxi license de-regulation | Panel
2017-05-05 | 7.5.2 | That the Commissioner considers how the issue of defective vehciles might be addressed | PCC
2014-04-11 | 8.7.1 | Update report to Panel on 101 call handling | PCC | 2017-09-01 | Deferred from Dec 16 - considered March 2017. Further update to come to Panel on this in 6 months
2017-03-10 | 8.4.1 | PCC to raise the issue of mutual aid for services for victims of crime through the APPC | PCC | 2017-09-01 | PCC to report back to Panel with an update in 6 months
2017-03-10 | 8.4.2 | Victim & Witness Commissioning Scrutiny - Further update in 6 months' time on progress, particularly on referral points, further development of video link facilities and further specialist training | PCC | 2017-09-01
2017-03-10 | 7.6.1 | Panel welcomed the improved figures for 101 call handling - further update in 6 months | PCC | 2017-09-01
2017-05-05 | 10.7.1 | That the PCC raise the issue of neighbourhood policing resources with the Chief Constable to understand how District Commanders are deploying officers within local areas and bring a report back to the meeting on 7th July. | PCC | 2017-12-15 | Verbal report give by PCC on 7 July 17. Further item on outcome of Neighbourhood Policing Review to go to Dec Panel
2017-07-07 | 10.13.2 | That Divisional Commanders be reminded of the need to make early communication with local councillors and to ensure prioritisation of contacts in the event of a local serious incident | Deputy Chief Constable | ASAP
2017-07-07 | 12.6.1 | That the COMs report referred to about the neighbourhood policing review be circulated to Panel | PCP Officer | 2017-07-01 | Circulated to Panel members
2017-07-07 | 13.2.1 | That the draft annual report be circulated for Panel's comments as soon as it is available and the final draft be considered at the Sept Panel meeting. | OPCC/PCP Officer | 2017-09-01
2017-09-15 | 2.3.1 | That the Commissioner reports back on the OPCC organisational review when it is complete | OPCC/PCP Officer | 3rd Nov 17 | Deferred to 3rd Nov 17
2017-09-15 | 8.5.1 | That the Commissioner continues to monitor 101 call handling performance and thanks Tom Donohoe on the work that has been done to improve performance so far | PCC
2017-09-15 | 11.8.2 | That the Commissioner brings back more detail on the numbers of arrest for terrorism offences in West Yorkshire | PCC |  | Figures for West Yorkshire not available. National figures circulated to Panel
2016-06-10 | 9.3.1 | That the Commissioner provides Panel with information on the Mediator pilot when it has been assessed. | PCC | 2017-12-01 | Dates to be confirmed by OPCC. Expressions of interest in the pilot and selection of an organisation to carry out the work is expected within the next 2 months. KL to keep Panel informed of timescales - 6 month pilot began in Sept 16
2017-03-10 | 5.19.2 | As part of the Delivery Quarterly - missing/absent data be revisted in detail in 6 months' time | PCC | 2017-12-15
2017-07-07 | 12.6.2 | That Panel receive an update on the outcome of the Neighbourhood review in November | PCC | 2017-12-15 | On agenda for December due to review timescales
2017-11-03 | 2.3.1 | That the PCC responds further to Cllr Tagg on the isue of the Force policy on low level drug dealing | PCC | end Nov
2016-09-09 | 10.6 | The PCC to keep Panel informed re: release of information contained within the investigation report of the now retired Chief Constable | PCC | ASAP | Raised again at Panel on 7 Oct 16. Still awaiting legal advice. Raised again on 16 Dec 16 & 5 May. Panel will be kept informed.
2017-11-03 | 10.6.2 | That the PCC ensures Panel is kept informed of the outcome of the Judicial Review by the former Chief Constable | PCC
2017-11-03 | 6.10.1 | That the PCC clarifies the number of Police officers recruited in the current financial year | PCC | 2017-12-01
2017-12-15 | 5.12.1 | That the PCC shares the impact asessments that have been undertaken with the Panel | PCC | 2017-02-01
2015-09-11 | 5.9.1 | The Commissioner to provide details of the Programme of Change’s review into internal shared services | PCC | 2018-03-01 | Consultation on business case for Fusion to be completed October 2017. To be picked up as part of Precept Commitment 4
2016-09-09 | 11.19 | Panel and CSPs sign up to Principles of Engagement | PCP | 2016-11-30
2016-12-16 | 8.2.1 | Update report on Pre-charge Bail to Panel in Dec 2017 following implementation of new legislation | PCC | 2018-03-01 | On the agenda for 9 March 2018
2017-03-10 | 6.7.1 | Out of Court Disposals - That the Commissioner brings an update report in 9/12 months, ensuring that it includes what organisation learning has been made and how this is used to improve the programme. | PCC | Dec17/Mar 2018 | On the agenda for 9 March 2018
2017-05-05 | 8.3.1 | That the Commissioner keeps Panel updated on any significant issues relating to the collaboration of blue light services | PCC |  | To be picked up as part of Precept Commitment 5
2017-11-03 | 10.6.1 | That the PCC reports back on how WY is addresing the HMIC recomnedations on Modern Slavery | PCC | 2018-03-01 | On the agenda for 9 March 2018
2017-11-03 | 10.6.3 | That the PCC reports back to a future meeting on the actions following the HMIC's letter re Abuse of position for a sexual purpose. | PCC | 2018-03-01 | On the agenda for 9 March 2019
2017-12-15 | 5.13.2 | That when the consultation is complete on the shift patterns, that Panel are provided with a briefing on how these will work. | PCC | TBA
2017-12-15 | 10.7.1 | That the PCC provide Panel with a copy of the report in response to the High Court Action as soon as it is available. | PCC | ASAP | Report is with the Legal Department at Wakefield Council - colleagues in Wakefield will be providing Panel members with a copy in due course
2018-02-02 | 8.2.1 | That the impact assessments for changes to neighbourhood policing be circulated to Panel as soon as possible | PCC | 2018-02-01 | Circulated to Panel 9th Feb
2018-02-02 | 10.1.1 | That Councillors Geraldine Carter and Steve Pullen sit on the Standards and Complaints Sub Panel with Councillor Alan Wassell as Chair | Police & Crime Panel Officer | 2018-03-01 | Meeting arranged for 19 Feb
2017-12-15 | 10.7.2 | That the PCC brings back a report on the NPAS review in the new year | PCC | Feb/March 18 | On the agenda for 20 April 2018
2017-05-05 | 6.5.1 | That Panel be updated on Re-Offending Strategy progress in due course and that the update includes an overview of the trend and interventions made around re-offender with identified mental health problems | PCC | Dec17/Mar 2018 | Panel received a copy of the draft strategy at the June 2018 meeting and commented on the content.
2018-03-09 | 6.10.2 | The PCC to revisit the historical consultancy report commissioned by the Police Authority looking at potential efficiences from regional collaboration | PCC | June 2018` | The OPCC have not been able to locate the report following the move from Police Authorities to PCCs but the recommendations from the report will have been followed when the report was first published and will likely have influenced decisions made in the proceeding years.
2018-03-09 | 12.5.1 | That the PCC look at convening a meeting of relevant stakeholders to ensure robust plans are in place for the knock-on effects of motorway closures affecting West Yorkshire. | PCC |  | This has been referred to the Safer Road Strategic Board which will ensure plans are in place.
2018-04-20 | 6.10.1 | That Councillor Lowe be included on the Criminal Health and Mental Health Forum | OPCC |  | Councillor Lowe added to the circulation list and dates of future meetings being sent.
2016-04-22 | 7.5.1 | ACC Battle invited a Member to link in with the Force's Positive Action work. | PCP | Ongoing | Panel member to volunteer - Cllr Amanda Pinnock has volunteered to link in with WYP and this is bring progressed
2016-11-04 | 5.8.1 | That the Commissioner provides further details on the process for an annual refresh of the Plan | PCC | 2018-07-01 | Draft of the refreshed Plan was shared and details on the process were considered at the June 2018 meeting. A formal response was received from the PCP and their suggestions were being considered with other feedback received from partners. The refreshed Plan was launched w/c 30 July 2018
2017-05-05 | 9.5.1 | That a report on the work of the BME Victim Champion Project be brought back to a future Panel meeting and that Saima Afzal be invited to present it | PCC | 2018-09-14 | Information on this project to be incorporated in to the Commissioning Update on the agenda for September 2018
2017-12-15 | 8.5.1 | To bring an update report on the progress of the implementation of recommendations from the Transformation Fund scrutiny review in 6 months | PCC | 2017-06-01 | Received at the July 2018 meeting
2018-06-15 | 9.31.1 | That the Commissioner further explores the impact of court closures has had on the levels of ineffective trial rates | PCC |  | Data has been supplied to the OPCC that supports the original response from the PCC that he did not believe there was a significant impact on ineffective trial rates due to court closures and if this had been the case the effect would have been evident in the early months following the closures in 2016.
2018-06-15 | 9.31.2 | That the PCC considers undertaking a campaign to raise the awareness of the 101 reporting on-line | PCC | 2018-09-14
2018-06-15 | 10.7.1 | The Panel agreed to publish a report outlining their full comments and recommendations to the PCC regarding the content of the draft refreshed Police and Crime Plan | Panel |  | Report sent to the PCC and published on Panel website
2018-06-15 | 11.12.1 | That the PCC considers the Panel's comments on the draft Reducing Re-offending Strategy | PCC |  | Comments from the Panel and all partners were considered before the strategy is finalised
2018-06-15 | 13.2.1 | That the PCC provides further information on the use of the Force crest on supermarket security vehicles | PCC |  | An approach was made to the Crime Prevention lead at WYP by Morrisons following them purchasing 2 CCTV vans for use within their car parks. They wanted to advertise a partnership approach with WYP with regards to crime prevention and keeping customers safe and proposed the purchase of 2 decals that could be applied to the vans when they were being used for this purpose only. A proposal was put to the PCC and the decision was agreed in April 2018 on the understanding use of the decal would be monitored so as not to be used when inappropriate.
2018-07-13 | 10.8.1 | That the PCC provides a report with more detail on actions being taken to address 101 demand and call handling for the next Panel meeting. | PCC | 2018-09-14
2018-04-20 | 6.10.2 | That the PCC looks at ways that better use of third sector/voluntary led facilities and services could be made | PCC | 2018-09-06 | To be picked up by the PCC's Criminal Justice and Mental Health Forum and on the agenda for the September meeting.
2018-04-20 | 8.7.1 | That the PCC brings the local Violent Crime Strategy to a Panel meeting when it is available | PCC | 2018-11-09 | Scheduled report to Panel's Nov 18 meeting
2018-09-14 | 10.8.1 | That the OPCC chase up the Link Officers to contact Link Panel members asap | OPCC | 2018-11-09 | October - All members have been contacted by the Lead Officers within the OPCC and arrangements for meetings are ongoing, have been agreed or have taken place.
2018-09-14 | 10.8.2 | That the PCC circulates information regarding activities for National Hate Crime week | OPCC | 2018-11-09 | A joint press release from WYP and the PCC was published which included details of specific activities organised by partners in each of the 5 districts. This is also attached as an appendix to the report on Hate Crime on November's agenda.
2017-11-03 | 5.13.2 | That the Panel is provided with information on the plans to move the Force from Good to Outstanding | PCC | TBA | PEEL Inspections report to go to Panel in July 18
2018-02-02 | 7.5.1 | That the PCC reports back to Panel as soon as information on the required efficiency targets for the 2019/20 settlement is clarified | PCC | 2018-12-14 | A report is scheduled for the December 2018 meeting
2018-07-13 | 5.9.1 | The PCC agreed to take on board Panel comments regarding the Annual Report | PCC |  | Panel comments were considered.
2018-09-14 | 5.20.1 | That the PCC meet with Bradford's Partnership locally to see what more can be done to improve feelings of safety | PCC | TBA | Some intial work is ongoing through the West Yorkshire CSP Forum to look at the results from the 'Your Views' survey which captures public perceptions and feeings of safety.
2018-11-09 | 10.10.1 | That PCP members urge support from their own LAs from the Gov on the issue of police funding | PCP members
2018-11-09 | 10.10.2 | That the PCC writes to the five Leaders setting out the funding position and seeking their support | PCC
2017-05-05 | 5.8.2 | That a further report on CRC's be brought to Panel when the full first year's figures are available in the autumn | PCC | 2019-03-01 | Update report to include implications of changes to CRC's to come to March meeting
2018-11-09 | 8.8.1 | That the PCC considers including an outcome to improve rates for transphobic hate crime continues ongoing work and engagement with the Trans community | PCC |  | Any changes or additions to the Police and Crime Plan would be considered as part of any future work to re-write or refresh the existing plan. The PCC and his staff are committed to ongoing engagement with the Trans community as part of ongoing business and delivery of the Police and Crime Plan
2018-12-14 | 10.2.1 | The PCC to circulate details of the district projects to be undertaken as part of the Early Intervention Youth Fund | PCC | 2019-04-01 | Paper to Panel meeting in April
2019-03-01 | 6.4.1 | Arrange a private briefing on the FMS prior tofull discussion at a future Panel meeting | OPCC/Panel Officer |  | Arranged to take place on 5 April
2019-03-01 | 11.3.1 | PCC to circulate the Reducing Re-offending summary leaflet to Panel | PCC |  | An electronic copy has been shared with the Panel Officer and copies will be available at the meeting on 5 April
2018-03-09 | 7.7.1 | That the PCC reports back addressing the issues raised following the Pre-charge Bail Post Implementation Review | PCC | TBA | Report going to July meeting
2018-07-13 | 6.8.1 | That the FMS be reported on to Panel in due course | PCC | 2019-04-01
2018-07-13 | 6.8.2 | The PCC provides further information on what framework is in place to address capacity and capability issues within safeguarding units | PCC | 2019-06-13 | Response: Co-ordinated through the Safeguarding Central Governance Unit, Districts have been engaged regarding their current and predicted demand. This demand includes ongoing non-recent historic enquiries. As a force we have then supplemented this anecdotal evidence and used it in combination with feedback provided by local subject experts alongside professional assessments of areas as identified as posing the greatest threat to the public to allocate additional resources to grow capacity and capability in a considered and proportionate manner. As a result of the growth posts funded through the local precept, District Safeguarding Units have seen additional investment of 58 FTE posts distributed across the five local policing districts
2018-09-14 | 7.5.1 | That the PCC continues to seek ways to improve keeping the public informed of progress on crimes and considers a scripted response on how to 'track my crime' upon calling the contact centre | PCC | 2019-06-13 | Response: Work has been ongoing to promote the 'track my crime function'. WYP currently hit over 5000 transactions per month on average on the track my crime function (peaking at 8748 in April) but it is expected that with the imminent introduction of enhanced functionality this will increase further, improving communication with the public and helping to respond effectively to increasing demand. We are ready to launch the new version of local crime tracker which will have an enhanced facility in allowing direct contact with the Officer in Charge. Corporate Communications are planning on an online summer pressures publicity campaign within which local crime tracker will take centre stage. The campaign will also feature on social media platforms, online and via an internal communications strategy.
2018-11-09 | 6.10.1 | The PCC to bring back a report on the impact of GANGBOs | PCC | 2019-09-13 | Ongoing and expected after the July meeting
2019-03-01 | 5.36.2 | PCC to provide information to the Panel as to where the SCF has been directed | PCC | 2019-06-14 | Report received at the June meeting
2019-04-05 | 9.8.2 | That the PCC thanks the Chief Constable for her dedicated work prior to her retirement at the end of the month | PCC | 2019-04-30
2019-04-05 | 9.8.3 | The PCC to keep Panel informed of the recruitment timetable. | PCC | 2019-07-19 | Confirmation Hearing scheduled for 19 July 2019
2019-06-14 | 14.2.1 | The Panel agreed that an update on the capacity and capability of safeguarding would be provided at the July meeting | PCC | 2019-07-01 | Provided under 6.8.2
2018-09-14 | 8.11.1 | That the Panel are provided with an estimated cost of the dealing with missing people in the context of the rest of the workload | PCC | 2019-09-13 | Ongoing and expected after the July meeting
2019-03-01 | 5.36.1 | Clarify the figures for the Hate Crime/Islamaphobia increases in West Yorkshire and bring back to Panel | PCC |  | Clarity is being sought on the comments made during the Panel meeting in March in order to provide the latest position.
2019-03-01 | 7.9.1 | That Panel members raise the issue of the re-design of probation with their local MPs prior to this being debated in Parliament | Panel members
2019-04-05 | 5.15.1 | That the PCC reports back on the EIY fund as part of the performance discussions. | PCC | 2019-11-01
2019-04-05 | 9.8.1 | That the PCC reports back on the additional funding announcements and what will be available to West Yorkshire when more detail is known | PCC |  | Verbal update at the 19 July meeting under 'Commissioner's response to any current issues'
2019-07-19 | 6.5.1 | The PCC to consider the inclusion of additional data in the annual report as set out at point 6.2. | PCC
2019-07-19 | 6.5.2 | The PCC to circulate details around the Community Alert system | PCC |  | Details circulated to Panel
2015-03-06 | 5.6.1 | That the Commissioner provides a report on the HMIC re-inspection of crime data integrity in due course. | PCC | June | Update August 2018: Confirmation of a further inspection has still not been received. Since March 2015, Panel have received a number of reports including during December 2015, July 2016 and a private briefing during October 2017. Reported to Panel, June 2019
2018-11-09 | 3.12.1 | PCC & Panel to revist CSE in Huddersfield in the New Year | PCC/PCP | 2018-03-01 | A private briefing on CSEA is being organised for later in 2019 as per the action from 01 March 2019 8.20.1
2018-11-09 | 5.4.1 | Panel to revisit NPT review when the full 12 month review is available | PCC | 2019-06-13 | Deferred to the September meeting
2019-03-01 | 8.20.1 | PCC to report back on reciprocal 'out of area' support for historical victims of CSAE | PCC | TBC | The response provided for 9.5.1 from September 2017 also covers this action.
2019-03-01 | 8.20.2 | PCC to provide data and evidence to demonstrate the impact that the PCC is making in terms of CSAE | PCC | TBC | Picked up as part of 8.20.3 from the 1 March 2019 meeting
2019-03-01 | 8.20.4 | To hold a private briefing session on aspects of CSAE | OPCC/Panel Officer | October | A private briefing was held during October 2019
2019-06-14 | 15.2.1 | That there would be a substantive item to focus on CSE at a future meeting. | PCC |  | A private briefing was held during October 2019. Prior to this a Priority Focus paper on CSEA had been considered at the March 2019 Panel meeting.
2019-06-14 | 2.3.1 | That the Panel agree to the co-option of an additional member subsequent to approval by the Secretary of State | PCP |  | Agreed by Home Office
2019-06-14 | 10.15.1 | That Kirklees best practice around bidding for funding from the SCF be considered for replication within other authorities | PCC/LA |  | There is an ongoing open offer for OPCC staff to work with Local Authorities and partners to increase or improve the quality of applications submitted for the SCF.
2019-09-13 | 2.3.1 | PCC to circulate final draft of the annual Report to members before it is published | PCC | ASAP | Members were provided a copy on the 10 October and invited to feed back.
2017-09-15 | 9.5.1 | That the Commissioner continues to try to progress a mutual aid agreement with other forces | PCC |  | As a general principle a victim would receive support in the area they are resident and would be referred to this service by the police force in whichever area the crime was committed. At present there is no mechanism to ensure support has been accessed or is being provided. The PCC has raised this issue through the Association of Police and Crime Commissioners (APCC) for further consideration.
2018-03-09 | 6.10.1 | The PCC to provide the Panel with details of what efficiencies NETIC aims to achieve along with other clear examples where financial savings are being realised | PCC | 2019-11-08 | A report was received at the 8 November meeting. A subsequent action for a further update in due course was agreed at Item 7.6.1
2019-06-14 | 8.3.1 | The Panel approved the request to recruit a second part time post to support the Police and Crime Panel Officer | PCP | Nov/Dec 19 | Recruitment to this post is ongoing.
2019-06-14 | 17.3.1 | PCC request further information around the expenditure of knife crime funding by other forces. This to be detailed in a substantive agenda item at a future meeting for comparison | PCC | TBA | A funding comparison table has been included in the Priority Focus paper on the agenda for the 20 December meeting
2019-11-08 | 11.2.1 | The Police and Crime Panel Officer to liaise with Panel members to seek an alternative meeting date to the 13th December | PCC | TBA | Meeting arranged for 20 December 2019
2019-11-08 | 13.4.1 | The Panel agreed that the original decision to uphold a complaint was supported. A letter to be written to the complainant explaining the Panel's final decision | PCP | TBA
2018-12-14 | 6.7.1 | The PCC to provide information on the numbers of under-represented groups in relation to detective applications and recruitment. | PCC | 2019-12-20 | Reported as part of paper covering the Precept Commitment 3 in December 2019.
2019-09-13 | 5.26.1 | The report on staffing/recruitment to include retention levels of BAME staff | PCC | 2019-12-20
2016-12-16 | 9.8.1 | Further update on Child Protection Re-Inspection following further HMIC Re-inspection | PCC |  | Update October 2019: details of any further inspection have not been received. No further inspection expected.
2018-06-15 | 9.31.3 | Invitation extended for any Panel member to visit the Customer Contact Centre and see the work that takes place. | Panel |  | A date is being progressed between the Panel Officer and the Contact Centre
2019-03-01 | 8.20.3 | PCC to bring back further detail on how 'the voice of the child' is being captured and used to improve strategy and service | PCC | TBC | This was picked up as part of 8.20.3 from the 1 March 2019 meeting - a public response is being prepared to share.
2019-03-01 | 8.20.5 | Add the Commissioning Strategy to a future agenda | OPCC/Panel Officer | 2020-07-01 | On the agenda for the July 2020 meeting
2019-06-14 | 7.12.1 | That the PCC reports back to Panel on the outcome of the Perpetrator Programme in due course | PCC | 2020-07-01 | Included in the Commissioning Update paper at the July 2020 meeting.
2019-11-08 | 5.26.2 | Further update to Panel on call handling at a future meeting | PCC | TBA
2020-02-28 | 6.2.2 | The PCC provide an update around the figures for Home Office funding when further information is released | PCC | TBA
2020-02-28 | 6.3.1 | That the Panel submit additional feedback on the Needs Assessment to the PCP Officer to be provided to the PCC for further consideration | Panel
2020-02-28 | 5.19.2 | That the PCC ensures that more detail of the outcome of the drink driving campaign is included as part of the Road Safety key priority report | PCC | 2021-03-01 | March meeting
2020-06-12 | 7.5.1 | Panel support the key changes to the refresh and will issue a report with detailed comments to the PCC as soon as possible. | Panel | ASAP | Report published on Panel website
2020-09-11 | 12.3 | That the Independent Panel member recruitment be postponed and existing appointments extended until at least May 2021 | PCP Officer | 2020-10-01
2020-10-09 | 3.1.3 | That the wording of paragraph 1a 8.1 of part 1 of the Panel Arrangements and Rules for the Conduct of Business be amended and replaced with: 1a.8.1 Independent Co-opted Members will be recruited and appointed for a term of office of four years, unless otherwise determined by the Panel in advance of the expiry of a term of office. | PCP Officer | 2020-10-01
2020-10-09 | 8.2.1 | That the PCC ensure Key Published Decisions are updated on his website before the next meeting. | PCC | 2020-11-01 | The website has been updated to 14 September. A number of agreed decisions relating to the Violence Reduction Unit are awaiting Home Office approval and will be published when this is received.
2020-10-09 | 11.3.1 | That a Complaints Sub-Panel be established to review the decision not to record a complaint from a member of the public. | PCP Officer | 2020-11-01
2018-03-09 | 8.4.1 | That the PCC reports back to Panel following the further work which is to be done to understand the implications of OoCDs and their effectiveness | PCC | 13 Nov 202 | To be picked up as part of a update paper on investigations, detections and outcomes - Feb Update - Panel and OPCC staff are looking at the content and timing of a report based on the recent PEEL inspection publication.
2018-09-14 | 5.20.2 | That Panel receive a paper on investigations and detection rates which explains the different outcomes and what is happening with the investigations review | PCC | 2020-11-13
2019-06-14 | 9.25.2 | Further details on the performance of 'outcomes of crime' should be brought to a future meeting. | PCC | 2020-11-13
2020-02-07 | 6.2.1 | The PCC report on accomodation for the future increase in Officers at a future panel meeting | PCC | 2020-11-01 | Included as part of the recruitment update in November
2020-02-28 | 5.19.3 | That the findings of the ‘Victim’s Journey’ review are reported to Panel in due course | PCC | 2020-11-01 | Included in the Investigations and Detections paper considered in November 2020
2020-06-12 | 9.10.1 | That the PCC provide a report to Panel to outline the measures that West Yorkshire Police take in order to meet the various challenges of racism in both the workplace and the community. | PCC | 2020-11-01 | Verbal update on activity to consider the issues at the September meeting
2020-10-09 | 5.9.1 | That the PCC review feedback on the Annual Report and include the accountability of the Chief Constable, by adding additional information gathered from the WYP accountability structure meetings. | PCC | TBA | The Annual Report will be published mid-December and the final draft shared with Panel Members - consideration for the comments made by Panel has taken place and changes made where appropriate.
2019-07-19 | 9.25.1 | The PCC to provide comparison on public satisfaction with other similar sized police forces. | PCC | TBA | Update included as part of the Delivery Quarterly paper in December
2020-02-28 | 5.19.1 | That the Panel are provided with detail around figures for fraud and forgery crime in West Yorkshire | PCC | TBC | Update included as part of the Delivery Quarterly paper in December
2020-09-11 | 5.18 | That the PCC look further into data on ASB in order to break down the proportion of previous societal occurrences and ASB attributed to Covid-19 and the resulting lockdown | PCC | TBA | Update included as part of the Delivery Quarterly paper in December
2020-09-11 | 5.19 | That the PCC provide further information around the percentage of Domestic Violence Protection Orders that had been breached | PCC | TBA | Update included as part of the Delivery Quarterly paper in December
2020-11-13 | 7.16.1 | The Chief Constable agreed to look into the issue of feedback from the CoP assessments to unsuccessful candidates and to feed this back to the PCC and Panel. | CC |  | Panel members contacted regarding the candidates concerned
2020-11-13 | 8.2.2 | That clarification is sought regarding the Panel’s power of veto on a proposed precept and the Briefing Book be amended accordingly. | PCP |  | Clarified that existing Panel powers continue and the briefing book has been ammended to reflect this
2020-09-11 | 6.6 | That the PCC consider amending the performance target ‘to increase visibility of frontline officers’ to include the proportion of BAME officers on the frontline to be reflective of the communities they serve | PCC | TBA | This will be reported as part of the Delivery Quaterly paper in March 2021
2021-03-19 | 8.9.1 | The PCC to provide an update to Panel Members on NPAS in due course. | PCC | ASAP | Update provided to Panel on issues raised by the media along with an outline of the process going forward. |  | Complete
2021-01-22 | 5.21.3 | Continue to build relationships between the CSP's and PCP and sign up to the Principles of Engagement | PCP/CSPs |  | All Panel members to link regularly with their CSP and the Chair or Deputy to attend each CSP annually |  | Complete
2018-04-20 | 5.21.1 | PCC to report back to Panel when the outcome of the NPAS new fleet business case is known | PCC | Unknown | In the PCP meeting on 19th March, the PCC confirmed that a meeting of the National Board had been held on 18th March 2021 and some key decisions had been made. He reported that a full business case was being worked up with Blue Light Commercial. The PCC agreed to provide a further update to Panel on NPAS when he was able to do so. |  | Complete
2019-09-13 | 5.7.1 | That the PCC provide further detail around the dip sampling of use of pre-charge bail and RUI referenced within the report to a future Panel meeting | PCC | July | As part of the investigations paper |  | complete
2020-11-13 | 8.2.1 | That the PCC provide further information regarding the transition of roles under the new Mayoral structure. | PCC | 2021-04-01 | The Managing Director of WYCA spoke to the PCP meeting on 23rd April to update Panel on the transition process. |  | Complete
2021-06-18 | 9.3.1 | That the Police, Crime, Sentencing and Courts Bill Overview be deferred to a future meeting and Panel write to the Mayor to explain the reasons for this. | Panel | 2021-06-01 | E-mail sent to the Mayor's office to explain the reason for the deferral |  | Completed
2020-11-13 | 6.10.1 | That the PCC and CC look at the way that outcomes information can be provided and how it can better reflect to the public the more positive picutre that had been indicated. | PCC/CC | July |  |  | Complete
2021-09-10 | 6.9.1 | The DMPC agreed to take on board Panel comments on the annual report | DMPC | 2021-11-01 |  |  | Complete
2021-09-10 | 7.10.1 | Panel members to share the Police and Crime Plan consultation as widely as possible in their local areas. | Panel | 2021-11-01 |  |  | Complete
2020-10-09 | 6.16.1 | The outcome of the work of the Equality and Diversity Task and Finish group and a resulting action plan be reported back to Panel when it is available. | Mayor / DMPC | Nov | Report to Nov meeting |  | Complete
2020-10-09 | 6.16.2 | That the PCC provide information on the numbers of mobile finger print scans along with case studies which would show that the use of this techology can be beneficial to the community. | PCC | 2022-03-01 | The Mayor reported to the 4th Feb meeting that WY Police have agreed not to automatically link biometric fingerprint data taken in WY to the HO database. |  | Complete
2021-01-22 | 5.21.1 | Raise the benefits of working across a wider geography and developing WY wide strategies which are implemented in an integrated way the with PCC and promote this under the new Mayoral arrangements | PCP | 2021-12-01 | To be considered as part of the development of the Mayor's new Police and Crime Plan |  | Complete
2021-03-19 | 6.6.1 | The PCC agreed to make contact with the Road Safety Partnership Manager to discuss access to decision makers. | Mayor | 2021-12-01 | The Mayor assured Panel that she would be looking into the arrangements for Road Safety going forward. Update to be included in Dec DQ |  | Complete
2021-12-17 | 5.4.1 | Panel noted the outcome of the PEEL report, congratulated WYP on their achievements, and acknowledged the identified areas for improvement | Mayor |  | Added to forward agenda plan for April for further report back on actions |  | Complete
2021-12-17 | 8.18.2 | That the Mayor considers Panel comments as the draft Police and Crime Plan is further revised | Mayor | 2022-01-01 | Final Plan to be launched on 9th March |  | Complete
2021-12-17 | 12.3.1 | That the revised draft Police and Crime Plan is circulated to Panel members as soon as possible to ensure they have sufficient time to consider it before providing final recommendations at the meeting in January | Mayor | 2022-01-01 | Plan circulated within required timeframe for comments. |  | Complete
2022-06-10 | 9.2.1 | Panel agreed the addition of new wording to clarify procedures when dealing with vexatious and repetitive complainants | PCP Officer | 2022-06-01 |  |  | Complete
2022-06-10 | 11.14.2 | Details of the Pol-Ed programme to be circulated to Panel members. | DMPC | TBC | Circulated |  | Complete
2022-06-10 | 11.14.1 | The Chief Constable to provide Panel with a timetable of dates for the force neurodiversity training, and for Panel to be provided with a legal definition of the term for their own clarity and information. | Chief Constable / DMPC | TBC | Circulated |  | Complete
2022-06-10 | 12.9.1 | The DMPC to obtain comparative figures for Scandinavian road deaths prior to the introduction of Vision Zero and share these with Panel. | DMPC | TBC | Circulated |  | Complete
2022-07-15 | 6.7.1 | The Mayor or DMPC to ensure that evaluation forms for drug and alcohol related projects under the Safer Community Fund are available to the Panel. | DMPC | Sept | Project summaries are available on the website |  | Complete
2022-07-15 | 7.8.1 | That Panel members re-share animation produced by the Mayor’s office to highlight signs of modern day slavery in their communities. | DMPC | asap | Circulated |  | Complete
2022-07-15 | 8.7.1 | The Mayor to share the response to consultation on Fire and Rescue governance with Panel | Mayor | asap | Circulated |  | Complete
2022-07-15 | 8.7.2 | The DMPC to share figures on police officer perpetrated domestic abuse, if she is able to do so | DMPC | prior to Sept meeting | Sensitive information as cases are live |  | Complete
2022-10-07 | 7.12.1 | The Mayor's Office to circulate the Force Management Statement Executive Summary to Panel members. | DMPC | asap | Circulated via email on 17th October |  | Complete
2022-03-11 | 5.16.1 | Data on Missing Persons to be provided additionally as a percentage of local authority populations. | DMPC | 2022-06-01 | To be included in Performace Monitoring from October onwards |  | Complete
2022-10-07 | 7.12.2 | The Mayor's Office to look into whether it is possible to devolve some speed enforcement powers to local authorities. | DMPC | TBC
2022-07-15 | 5.19.1 | That the DMPC provides Bradford, Calderdale, Kirklees and Leeds local authorities with the committed numbers of new frontline police officers they can expect for their area. | DMPC | prior to Sept meeting | Provided at the November Panel meeting |  | Complete
2022-10-07 | 5.13.1 | The Mayor to liaise with the Chief Constable to acquire figures on re-offending rates with respect to the restorative justice section. | Mayor | TBC | Established that this data is not compiled, however, victim satisfaction information is available. |  | Complete
2022-10-07 | 5.13.2 | The Mayor to incorporate the further Panel feedback into the Annual Report, where possible. | Mayor | asap | Requests incorporated as far as possible - see additional appendix for more detail |  | Complete
2022-10-07 | 6.5.1 | The Mayor to share the Home Office letters which detail the governments long term strategy for Violence Reduction Units. | Mayor | asap |  |  | complete
2022-11-04 | 5.11.1 | The Mayor to look at including the need for more reporting of crimes against women and ensuring that there are the mechanisms in place to encourage this | DMPC | 2022-11-01 | For inclusion in Safety of Women and Girls Strategy
2021-01-22 | 5.21.2 | Panel to continue to monitor and share information with CSPs on the impact of the changes to the nature of ASB | PCP/CSPs | 2022-03-01 | Possibly arrange an additional meeting due to full agendas |  | Complete
2022-12-09 | 2.2 | That the Mayor pass figures on the take-up of the Ask Angela scheme to Panel members when data received from the CSPs | Mayor |  | Reported to Panel |  | Complete
2022-12-09 | 8.7.1 | The Deputy Mayor to consider including examples of proposed spend in the consultation questionnaire, and to simplify language where possible. | DMPC | TBC | Survey undertaken Dec 22/Jan 23 |  | Complete
2022-03-11 | 7.7.1 | DMPC looks further at the information provided to members of the public with a view to helping them better understand the complaints process. | DMPC | 2022-06-01 | WYP have updated the complaints page on their website providing a number of different options for complaints to be made: https://www.westyorkshire.police.uk/about-us/our-standards/professional-standards/making-complaint WYCA have also updated detail around the complaints procedures including a number of FAQ’s: https://www.westyorks-ca.gov.uk/policing-and-crime/complaints-and-conduct/ |  | Complete
2022-04-08 | 9.3.1 | That the Deputy Mayor brings a report to a future meeting regarding early intervention work, including benefits and what is working well, along with further detail of Positive Futures. | DMPC | 2023-04-01 | Making a complaint ¦ West Yorkshire Police |  | Complete
2022-10-07 | 7.12.3 | The Forward Agenda Plan to include a report on serious road traffic incidents within the next six months. | DMPC | 2023-07-01 | A full Road Safety paper was brought to the panel in April 2023. The paper was authored by the new Policy Manager for Vision Zero at the Combined Authority and included various elements around those Killed and Seriously injured on the road of West Yorkshire. |  | Complete
2022-10-07 | 8.5.1 | An item showing progress in Investigations and Outcomes to be added to the Forward Agenda Plan. | DMPC | 2023-03-01 | WYCA have also updated detail around the complaints procedures including a number of FAQ's. These changes can be seen on the below link: |  | Complete
2022-11-04 | 5.11.2 | That the Mayor writes to local authority Licensing Committees, encouraging them to read and implement the recommendations of the HO Select Committee report on spiking | DMPC | TBC | This action has been completed through the CSP Forum |  | Complete
2022-12-09 | 6.6.1 | The Deputy Mayor to include comparisons with similar police forces in future performance monitoring reports. | DMPC | 2023-03-01 | To be included from March 2023 |  | Complete
2022-12-09 | 6.6.2 | West Yorkshire Police to explore if there is a significant reason why more women than men report cyber crimes. | DMPC | TBC | To note: the same gender split does appear nationally. There are papers on the gov.uk website which break down the data further and this may perhaps provide more context than we are able to provide at a West Yorkshire level. https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/118469/fraud-typologies.pdf |  | Complete
2022-12-09 | 12.1 | A further financial update to be scheduled for September 2023. | Mayor | 2023-09-01 | A further financial update is scheduled for the Panel meeting in November 2023. |  | Complete
2023-03-10 | 5.18 | The HMICFRS evaluation report to be shared with Panel members. | Mayor | 2023-04-01 | Evaluation of the HMICFRS joint custody inspection programme - His Majesty’s Inspectorate of Constabulary and Fire & Rescue Services (justiceinspectorates.gov.uk) |  | Complete
2023-04-21 | 5.8.1 | The Deputy Mayor to show speed related offences as detailed in 2.17.6 of the Road Safety report, as a percentage of the local authority's population. | DMPC | 2023-06-01 | This action was completed in June 2023 and the detail provided to the panel. |  | Complete
2023-06-09 | 11.14.1 | The Mayor to look at adding a link to report sexual offences on the relevant part of the Combined Authority website. | Mayor | 2023-08-01 | This has been discussed at length with WYP and this is not possible as WYCA cannot take reports of sexual offences. Further work is ongoing relating to the reporting of sexual offences but this is captured under a further action raised at the same panel meeting. |  | Complete
2023-06-09 | 11.14.3 | The Police and Crime Panel Officer to liaise with WYCA to discuss the Mayor's Inclusivity Champion attending a future Panel meeting. | SW | 2023-07-01 | Inclusivity champion attended July meeting when EDI paper was discussed |  | Complete
2023-06-09 | 11.14.4 | The Mayor's office to provide Domestic Abuse reports as a per capita figure in future reports. | Mayor | TBC | This action is noted and the data is included in the Performance Report at the Panel in September 2023 |  | Complete
2023-07-14 | 8.6.1 | Panel Members to share the link to the Your Views survey within their contacts and networks. | Panel members | 2023-07-01 | Link provided and Panel members were asked to asked to share with contacts |  | Complete
2023-07-14 | 7.2.1 | Interested Panel Members to be linked to thematic leads within the Mayor's office to enable understanding and monitoring of individual areas of the Delivery Plan. | SW / Panel members | TBC | Panel members awaiting contact from relevant link officers |  | Complete
2023-09-08 | 6.17.2 | The Deputy Mayor to update Panel on the current situation regarding WYP's management of the NPAS service. | DMPC | 2023-12-01 | Update provided in November meeting, with further ones to follow |  | Complete
2023-03-10 | 7.7.1 | A video supporting the 'Speak Up Leeds' campaign to be circulated to Panel members. | Mayor | 2023-04-01 | Circulated to Panel members November 23 |  | Complete
2023-06-09 | 11.14.2 | The Deputy Chief Constable to look at how to make reporting sexual offences easier via the WYP website. | DCC | TBC | Website been reviewed and improved |  | complete
2023-07-14 | 6.12.1 | The Deputy Mayor to look at ways of promoting the 24/7 Rape and Sexual Abuse Support Line in West Yorkshire. | DMPC | 2023-08-01 | WYCA Comms Team will be highlighting this during Violence Awareness week 5-11 Feb |  | Complete
2023-11-10 | 5.6.1 | The Director of Finance and Commercial Services to amend the report to i) continue to show two separate lines for PFI, and Rent and Rates, and ii) provide clarification around the references to "75p income loss and CT support", before the final version of the report comes to Panel in February. | DFCS | 2023-02-01 | This is being completed and will feature in the Precept paper |  | Complete
2023-11-10 | 7.12.1 | The Deputy Mayor to provide the following breakdowns of information from this year's consultation survey: ethnicity, return rate of the postal survey and responses by method. | DMPC | 2024-02-01 | This information is provided as part of the Precept paper 24-25 in Appendix A - Survey Results |  | Complete
2023-12-08 | 5.6.4 | The Deputy Mayor to include actual numbers of respondents to the precept consultation survey in 2023, in the report. | DMPC | TBC |  |  | Complete
2023-12-08 | 5.6.2 | The Deputy Mayor to give context to the data on domestic abuse in the Annual Report, alongside expanding on the work of the CARA programme. | DMPC | TBC |  |  | Complete
2023-12-08 | 5.6.3 | The Deputy Mayor to amend the narrative around the Positive Futures Youth Intervention scheme to reflect the inclusion of all five local authority areas. | DMPC | TBC |  |  | Complete
2023-12-08 | 8.7.1 | The Deputy Mayor to look at the possibility of IDVAs and ISVAs collecting data on victim engagement in the criminal justice process. | DMPC | TBC | This has been looked into and an explanation sent to panel alongside the action log on 13/05/2024 |  | Complete
2024-03-01 | 8.9.1 | The Mayor's Office to share the completed victims and witnesses strategy when it is published in April. | DMPC | TBC | Item has been shared with Panel |  | Complete
2023-09-08 | 6.17.1 | That the Deputy Mayor provide Panel with a paper which sets out the assurances she has had that the Force’s senior officers understand and are aware of any issues of negative behaviour and culture in WYP such as those identified in the Casey report. It was requested that the paper additionally shows how the Mayor’s office triangulate any concerns raised directly with them | DMPC | 2024-03-01 | Assurance paper provided at March 24 panel |  | Complete
2023-09-08 | 5.16.2 | The Deputy Mayor to check if any issues have been flagged around the upcoming transition from analogue to digital landlines, which could affect 999 call answering times. | DMPC | 2023-12-01 | Verbal update given by both DMPC and CC |  | Complete
2023-09-08 | 5.16.1 | The Deputy Mayor to provide a further breakdown of ethnicity statistics, focussing on senior roles at West Yorkshire Police. | DMPC | 2023-12-01 | Provided in Dec 23 |  | Complete
2023-03-10 | 7.7.2 | A breakdown of grant money per district to tackle anti-social car crime to be circulated. | Mayor | 2023-04-01 | Up-to-date data for this will be provided at the July panel in the Neighbourhood Crime and ASB paper |  | Complete
2023-11-10 | 9.2.1 | A item on online harm intervention to be added to the Forward Agenda plan. | SW / Mayor's Office | TBC | Pencilled into forward plan for July |  | Complete - covered at July meeting
2024-03-01 | 7.12.1 | A breakdown of recorded incidents on the use of force in custody and community settings to be provided by West Yorkshire Police. | WYP / Mayor's Office | TBC | Intended for June 24 COM paper. Update will follow. |  | Complete - provided by LK on 1 August
2024-04-12 | 6.8.3 | The Deputy Mayor to share information about the Herbert protocol, for onward sharing by Panel members. | DMPC |  | Information sent to Panel |  | Complete
2024-02-02 |  | Precept Commitment 1: Commence early discussion with Panel about the quality, content and format of future budget consultations. Set up a small working group with Panel members to look at best practice across other PCC areas with the aim of providing the public with more detail of the implications of different funding options. | Mayor | 2024-11-01 |  |  | Complete
2024-02-02 |  | Precept Commitment 2: Provide the Panel with a report back on Priority Based Budgeting to assure them that required efficiencies are on track in line with projections to meet future funding shortfalls. | Mayor | Further detail by Feb 25 | The DMPC agreed to provide Panel with more information on PBB and the progress on the work to close the financial gap as part of the precept process. |  | Complete
2024-02-02 |  | Precept Commitment 3: To report back mid-year on the reserves position providing assurances that these are kept at a sustainable level. | Mayor | 2024-11-01 | Further detail to be provided by February 2025 |  | Complete
2023-07-14 | 5.10.1 | The Deputy Mayor to provide data on stop and search for the 14-20 age group. | DMPC | Early 2025 | Being looked at as part of the performance refresh in the new Police and Crime Plan |  | Complete
2023-12-08 | 7.11.1 | The Deputy Mayor to include population data for context, and age alongside KSI indicators going forward. | DMPC | 2024-12-01 | Information was provided as part of the Road Safety Update in April 24. Performance meassures are being looked at as part of the new Police and Crime Plan |  | Complete
2024-03-01 | 5.15.1 | WYP to provide clarification on the numbers of frontline officers and staff who have been recruited since 2021, including a breakdown by ethnic minority groups where possible. | WYP / Mayor's Office | 2024-12-01 | Further information provided on 5 December with ethnicity breakdown included - information with Panel for comment and any further questions |  | Complete
2024-04-12 | 6.8.2 | The Deputy Mayor and WYP to discuss alternative ways that performance around missing persons could be measured. | DMPC | 2024-12-01 | Panel will be notified when a discussion has taken place This has been requested for the next Performance Scrutiny Meeting |  | Complete
2024-09-13 | 6.14.1 | The Mayor’s office to check the figures relating to current numbers of officers from ethnic minority backgrounds, along with the data provided on DA incidents and repeat victims. | Mayor's Office | 2024-12-01 | Further request following initial information provided in the context of 5.15.1 - This has been noted and will be updated for the next performance report. |  | Complete
2024-11-08 | 5.12.1 | The Deputy Mayor to consider the recommended inclusions to the Annual Report. | DMPC | 2025-01-01 | The recommended inclusions have been considered and the final version of the report is expected to be completed in 2024. Hard copies will be handed to Panel members at the February meeting |  | Complete
2024-11-08 | 6.9.2 | The DMPC agreed to provide Panel with more information on PBB and the progress on the work to close the financial gap as part of the precept process. | DMPC | 2025-02-01 | Further detail to be provided by February 2025 |  | Ongoing
2024-11-08 | 7.9.1 | That the Mayor and her team incorporate some of the feedback and learning from other police areas into the narrative and endeavour to launch the consultation immediately after the funding settlement is announced | Mayor/ DMPC | 2024-12-01 | An update on the Precept Consultation will be given at the December Panel meeting |  | Complete
2024-11-08 | 10.2.1 | That the DMPC address outstanding items within the Agreed Actions Log including clarification on the numbers of frontline officers and staff who have been recruited since 2021 also broken down by ethnic minority groups where possible, to be added to a future Panel agenda. | DMPC | 2024-12-01 | Ethnic minority breakdown for new recruits provided on 5 December - circulated to Panel with papers for meeting for any comment or further questions. |  | Complete
2024-12-13 | 6.12.1 | Panel to submit a report to the Mayor setting out their agreed views and recommendations on the draft Police and Crime Plan. | Panel | 2024-12-01 | Report published along with the Mayor's response on the Panel website |  | Complete
2025-04-11 | 8.2.1 | The Deputy Mayor to confirm the threshold at which Key Decisions are published on the Combined Authority’s website. | DMPC | 2025-06-01 | For transparency all decisions relating to Policing & Crime and VRP are published on the website unless the Record of Decision states they are ‘Sensitive’ under the GSC Scheme or Exempt under 2(2) of the Elected Local policing Bodies (Specified Information) Order 2011. |  | Complete
2025-04-11 | 9.2.1 | The Deputy Mayor to provide further data on WYP training completion rates for circulation amongst Panel members prior to the next scheduled meeting on 13 June. | DMPC | 2025-06-01 | WYP have provided the following figures for training completion rates Strategic Workforce Planning searched for all student Officers on cohorts due to complete their training in 2024 and whether they were still working for WYP. 442 are still working for West Yorkshire Police which is a completion rate of 81% Any further detail on this would have to be via a manual audit and as such a considerable piece of work |  | Complete
2025-03-07 | 7.14.1 | The DMPC to ciculate the IOPC national stop and search learning report from 2022 | DMPC | 2025-03-01 | Circulated 7th March 2025 |  | Complete
2024-07-12 | 5.7.1 | The Deputy Mayor to provide further data on WYP training completion rates. | DMPC | 2025-04-01 | Figures provided before 13 June meeting |  | Complete
2024-09-13 | 5.18.1 | The Deputy Mayor to provide further data on WYP training completion rates. | DMPC | 2025-04-01 | Figures provided before 13 June meeting |  | Complete
2024-04-12 | 8.3.1 | An update on the implementation of the new PDR system (Force IDM) within WYP to be added to the forward agenda plan for autumn 2024. | SW / Mayor's Office | 2025-03-01 | Update given as part of the PEEL report to panel at the April 2025 meeting - see minutes 5.4 - report timetabled for November meeting - see 5.10.1 April 2025 |  | Complete
2024-07-12 | 6.9.1 | The Deputy Mayor to look at providing comparisons to other Forces around the profile of ASB. | DMPC | 2024-12-01 | This information will be available as part of the Neighbourhood Policing Guarantee data produced for the Home Secretary |  | Complete
2024-12-13 | 5.14.2 | The Mayor agreed to provide written feedback to Panel on the WYCA survey which monitor’s cyber-attacks on businesses. | Mayor/ DMPC | 2025-03-01 | Meeting took place with WYCA business group - the cyber attacks are not included on the survey, but will be discussed within an agenda item at the next meeting. |  | Complete
2025-06-13 | 10.2.1 | The Deputy Mayor’s office to provide details of the company who have secured the contract for the Your Views survey when appropriate to do so. | DMPC | 2025-09-01 | Company name will be shared at the next meeting following the start of the contract (likely September) |  | Complete
2025-07-11 | 5.10.1 | The Deputy Mayor to circulate high level plans for the Summer Surge to Panel members. | DMPC | 2025-07-01 | Circulated by email on 25 July |  | Complete