## Outstanding
West Yorkshire Police and Crime Panel Agreed Action Log | [6 empty] | Item 12
Date | Item | Agreed Action | Attributed to | Date for completion | Action undertaken | Action undertaken | Status
2016-02-06 | 6.1 | Precept Commitment 1: Recruit 300 new police officers and provide regular updates to Panel on the progress of this recruitment. | PCC | Ongoing | Regular updates to Panel on progress. First update scheduled for 10 June 16. Moved to 15 July due to size of the agenda.
2016-02-06 | 6.1 | Precept Commitment 2: Protect PCSO numbers (565) | PCC | Ongoing | Include PCSO retention / recuitment as part of police officer recruitment update. First update on 10 June 16. Moved to 15 July due to size of the agenda.
2016-02-06 | 6.1 | Precept Commitment 3: The PCC to provide further detail on workforce plans and how resources will be deployed, managed and developed to ensure VfM | PCC | Ongoing | First update in September. Panel requested in-depth briefing to a future meeting on 11 Mar 16. Private briefing in Sep 16.
2016-02-06 | 6.1 | Precept Commitment 4: Provide oversight of the BME Action and Evaluation Plan along with regular updates on its implementation to ensure diversity. | PCC | Ongoing | Include within the police officer recruitment report. First update on 10 Jun 16. Moved to 15 July due to size of the agenda.
2016-02-06 | 6.1 | Precept Commitment 5: Provide details on the budget plans to manage any potential deficit for 17/18 | PCC | Ongoing
2016-02-06 | 6.1 | Precept Commitment 6: Ensure that information relating to commissioned services is transparent and provided to Panel | PCC | Ongoing | Part of the scrutiny review of commissioned services for victims and witnesses
2015-09-11 | 5.9.1 | The Commissioner to provide details of the Programme of Change’s review into internal shared services | PCC | Update in spring 2017 | Katherine Johnson to confirm timescales. Timescales are not yet available (28/10). Not included within Transformation Fund report on 15 Jul 16. Part of 'Fusion' which is a wider review of all back office functions. Completion of Fusion to be confirmed by WYP. KJ to update Panel in due course - anticipated update in Spring 17
2016-03-11 | 12.1.1 | Officers to work together to propose a final version of the Memorandum of Understanding | PCP/PCC | 2016-09-09 | Panel Officers to draft MoU and liaise with OPCC. Sam liaising with Trish and Bernadette (13 Oct 16)
2016-06-10 | 9.3.1 | That the Commissioner provides Panel with information on the Mediator pilot when it has been assessed. | PCC | 2016-10-07 | Dates to be confirmed by OPCC. Expressions of interest in the pilot and selection of an organisation to carry out the work is expected within the next 2 months. KL to keep Panel informed of timescales once the pilot has begun (17/02/16)
2015-11-13 | 6.4.2 | Out of Court Disposal Pilot – that the Commissioner provides a report to the Panel on the pilot the new out of court disposals in West Yorkshire | PCC | 2017-02-01 | Deferred from 6 Mar 15 agenda by Chair of Panel. OPCC to provide a briefing of the scope of the pilot outside of the meeting. Formal report after pilot ends in Nov 15. Formal report on the pilot not explected until late June 2016 so suggestion paper is brought to Sept meeting (26/02). Nothing yet from MoJ - now moved to Nov 16 meeting. |  | Ongoing
2014-11-07 | 7.4.1 | That the Commissioner look further into this issue (use of police bail) and come back to the Panel within the next six months with an action plan addressing any necessary improvements. | PCC | 2016-12-16 | Report back to go to Panel meeting along with Temporary Chief Constable in October. Report to the October meeting – Completed. Requested update in 6 months. To include WYP's response to the new bail measures time limit of 28 days. Six month update required. Further six month update required in April 16. Particular reference to improvements in gathering technical and medical evidence. Further 6 month update required following Bail Act |  | Ongoing
2014-04-11 | 8.7.1 | Update report to Panel on 101 call handling | PCC | 2016-12-16
2016-03-11 | 11.5.2 | Update report on progress against the recommendations made by HMIC in their Child Protection Post-Inspection Review report | PCC | 2016-12-16 | Report to Panel on Commissioner's actions
2016-03-11 | 6.11.1 | That the Force re-run the exercise to compare the numbers of people on extremely long-term bail periods and the numbers actually charged with an offence on a District basis and report this back to Panel in due course. | PCC | 2016-11-04 | Include this as part of the bail report in Nov.
2016-04-22 | 1.5.3 | The Commissioner to provide a report to a future Panel meeting on what actions WYP will be taking around disciplinary hearings for senior police officers in public. | PCC | 2016-11-04 | Panel wants to know the process
2016-06-10 | 14.7.1 | That the Commissioner provides a report to the Panel within six months on the progress made against the recommendations highlighted within HMIC’s Crime Data Integrity report. | PCC | 2016-12-31 | Reported to 6th March. Further report to come back to Panel following HMIC re-inspection. T/CC Collins provided private update following Panel meeting on 12 June 15. On agenda for Dec 15. No re-inspection, HMIC ad-hoc inspections in 2016. 6 month update in July 16. Future report to follow the ad-hoc HMIC inspection in 2016. |  | Ongoing
2014-09-12 | 5.7.2 | ACC Battle invited Members to visit the ANPR Control Room | PCP | 2016-12-31 | Any member wishing to do so should contact Panel Officers. Relevant to the Transformation Fund scrutiny review.
2016-04-22 | 7.5.1 | ACC Battle invited a Member to link in with the Force's Positive Action work. | PCP | Ongoing | Panel member to volunteer
2016-07-15 | 5.7.1 | That the Panel be provided with a breakdown of police officer applicants by age | PCC | 2016-11-04 |  |  | Completed
2016-09-09 | 5.7.2 | That the Panel be provided with information re: police officers on restricted / recuperative duties over time. | PCC | 2016-11-04 |  |  | Completed
2016-09-09 | 6.8 | The Panel provides the PCC with information on where data sharing had been a problem amongst partners | PCP | 2016-11-04 | Cllr Hussain has provided clarification to the OPCC who have raised with WYP. Rob to update in due course (20 Oct 16).
2016-09-09 | 7.4 | PCC's Commissioning Group to consider the Panel's Scrutiny Review of Commissioned Services | PCC | Ongoing PCC to report back in March 17 | Jo Sykes attended the Commissioning Group meeting and outlined the review. The Deputy Treasurer agreed to consider the recommendations. Jo Sykes to feedback to the Panel. Commissioner to report back to Panel in 6 months
2016-09-09 | 8.3 | The PCC ensures that key and delegated decisions are recorded in a timely manner | PCC | Ongoing | Susan Field to manage this.
2016-09-09 | 10.6 | The PCC to keep Panel informed re: release of information contained within the investigation report of the now retired Chief Constable | PCC | 2016-11-04 | Raised again at Panel on 7 Oct 16. Still awaiting legal advice. Panel will be kept informed. |  | Completed
2016-09-09 | 10.7 | Chair / Vice Chair attend CSP meetings | PCP | 2016-11-04 | Panel Officers to arrange with CSPs |  | Ongoing
2016-09-09 | 11.19 | Panel and CSPs sign up to Principles of Engagement | PCP | 2016-11-30 |  |  | Ongoing
2016-09-09 | 11.2 | Leeds Scrutiny Board to consider the Panel's scrutiny review into commissioned services | Angela Brogden | 2016-12-31
2016-09-09 | 12b.4 | That the Commissioner provides a written response to the Panel's scrutiny review | PCC | 2016-03-10 | Formal report back to Panel with an update on how recommendations are being implemented.
2016-10-07 | 7.4.2 | PCC to try to ensure that the Priority Plans to support the Police & Crime Plan are completed by the end of December | PCC | 2016-12-31
2016-10-07 | 5.8.1 | That the Commissioner provides further details on the process for an annual refresh of the Plan | PCC | 2016-03-10
2016-11-04 | 5.8.2 | Panel to produce a formal report with detailed recommendations following review of draft Plan | PCP Secretariat | 2016-11-08 | Report with recommendations sent to PCC and published. Response from PCC received and published |  | Completed
2016-11-04 | 5.8.3 | PCC keep Panel updated on the latest position regarding the Funding Formula review and consults with Panel when proposals are available | PCC | 2016-03-10 | PCC to consult with Panel when proposals are available for consultation - expected around Mar 17
2016-11-04 | 6.8.1 | PCC to keep Panel informed of any developments around the 17/18 provisional settlement | PCC | 2016-12-31
2016-11-04 | 6.8.2 | PCC to bring a more detailed report to the next meeting providing a comprehensive update on actions taken and next steps in implementing HMIC recommendations, also to include how the PCC is holding the CC to account and monitoring improvements | PCC | 2016-12-16
2016-11-04 | 7.3.1 | PCC to keep Panel informed of any changes made around the publication of key decisions | PCC | ongoing
2016-11-04 | 9.3.1 | That if information is requested in public, the response should also be in public | OPCC/PCP Secretariat | ongoing
2016-11-04 | 10.4 | PCC to bring a report to the Panel on what actions he is taking to mitigate any safeguarding risks as a result of the de-regulation of taxi licensing | PCC | 2017-03-01
2016-11-04 | 11.6.2 | PCC to ensure that papers include the author and contact details and are sent to the PCP on time | PCC | ongoing

## Completed
West Yorkshire Police and Crime Panel Action Log
Date | Item | Agreed Action | Attributed to | Date for completion | Action undertaken | Status
2014-11-07 | 7.5.1 | That the Commissioner provide panel with details of the terms of reference and scope of the governance review which is currently being undertaken | PCC | ASAP | COMPLETED | C
2014-12-12 | 6.3.4 | That the Panel writes to the Home Office re: Panel’s powers in the complaints process | PCP Officers | ASAP | COMPLETED | C
2014-12-12 | 6.3.5 | That the Panel writes to the PCC re: the complaints process to ensure that complainants are regularly updated | PCP Officers | 2014-12-19 | COMPLETED | C
2014-12-12 | 7.9.1 | That the Panel writes to the PCC re: the recommended appointment of Katherine Johnson to the Treasurer post | PCP Officers | 2014-12-19 | COMPLETED | C
2015-03-06 | 10.2 | PCP Officers to provide members with the latest version of published key decisions from the Commissioner's website | PCP officer | ASAP | COMPLETED
2015-01-15 | 1.5 | PCP Officers to email Members with Dave Livesey biog | PCP Officers | 2015-02-16 | COMPLETED
2015-01-15 | 3.3 | PCP Officers to draft key questions for Dave Livesey on the Government's response to the Home Affairs Select Committee report on PCCs | PCP Officers | 2015-02-26 | COMPLETED
2014-12-12 | 15.4.1 | That the PCC brings a report on 101 call handling to a future meeting and provides reasons to the Panel why WYP did not respond to the BBC’s FOI request | PCC | 2015-03-06 | COMPLETED
2014-11-07 | 12.5.1 | That the Joint Independent Audit Committee considers crime data integrity and the strategic workforce plan as part of their work programme. | Trevor Lake, Joint Audit Committee | Ongoing | This is being considered by AC. Removed from PCP action list. COMPLETED
2015-03-06 | 16.2.1 | That a complaints Sub- Committee meets to consider the appeal regarding the non-recording of a complaint | PCP Officer | 2015-03-18 | COMPLETED
2014-12-12 | 9.6.1 | That the PCC updates Panel on the progress of business cases | PCC | 2015-04-24 | Duplicate Action. Removed from Action Log.
2014-12-12 | 9.6.3 | Paul Whiteley to attend a future meeting of the Panel re: transformation fund projects | OPCC | 2015-04-24 | Duplicate Action. Removed from Action Log.
2014-12-12 | 9.6.2 | That the PCC ensures that Transformation Fund projects are reviewed and expected outcomes are monitored and measured | PCC | Ongoing | Duplicate Action. Removed from Action Log.
2014-12-12 | 8.7.1 | That the PCC shares the Estates Strategy with the Panel | PCC | 2015-10-09 | Duplicate Action. Removed from Action Log.
2014-11-07 | 5.7.1 | That the Commissioner brings a report on the strategic workforce plan to a future meeting of the Panel. | PCC | 2015-10-09 | Duplicate Action. Removed from Action Log.
2014-11-07 | 5.7.2 | That the Commissioner provides information to the Panel on the status of the review of the Divisional Resourcing Model. | PCC | 2015-04-14 | PCC explained Ward Based Needs Assessment took place not a review of the Divisional Resourcing model. Information to be shared outside of the meeting cycle. Still awaiting comparative info. Requested from OPCC several times. KL to speak to MBW re: discussing this with AL at tje 1:1 on 14 April. MBW reluctant to share figures as political. Description of method sent to Members on 17 April 2015. COMPLETED
2015-01-15 | 7.6 | Martin Goldman of the CPS to be invited to attend the Panel meeting when LCJB performance data is presented | LCJB | 2015-04-24 | Geoff Dodd has agreed to write the performance report. Geoff Dodd and / or Martin Goldman to attend. KL to confirm that Geoff Dodd is attending. Geoff Dodd attended. COMPLETED
2014-09-12 | 10.8.1 | That a report giving a progress update on all the individual recommendations from the DIP review are brought to a future meeting. | PCC | 2015-04-24 | Request for the DIP funding to be allocated based on population and crime stats. Take into account the address of the perpetrator which may be different from the district the crime was committed in and how funding is allocated to cover this. COMPLETED
2015-03-06 | 7.4.1 | Commissioner updates Panel on whether WY Police places callers on hold upon answering their call. | PCC | 2015-04-24 | Update under Matters Arising from the minutes COMPLETED
2015-03-06 | 12.5.1 | That the Commissioner provides information on the Force's use of RIPA to hack into phones | PCC | 2015-04-24 | KL to provide response to PCP officers prior to the next Panel meeting.
2015-03-06 | 12.5.2 | That the Commissioner provides information on the number of police officers who resigned whilst being subject to misconduct investigations | PCC | 2015-04-24 | KL to provide response to PCP officers prior to the next Panel meeting. COMPLETED
2014-11-07 | 7.5.2 | That the Commissioner report back in due course on the governance review of the Force which is nearing completion | PCC | 2015-04-24 | OPCC to confirm. Panel had some information from Isabel on 15 Jan 15 the PCC's governance review but no detail on the Force's. KL to speak to the Force and update Panel. Unsure as to whether the Force has undertaken a separate governance review. KL stated that the Force has not undertaken a separate review. COMPLETED
2015-04-24 | 15.2.1 | PCP Officers to work with the OPCC with a view to changing the date of the July meeting | PCP Officers | 2015-05-08 | ED confirmed PCC availability on 10 July. Currently checking availability of Panel Members. Meeting remains as 17 July due to diary commitments. COMPLETED
2015-04-24 | 16.1 | Cllr Lowe stated that she would write to Cllr Les Carter on behalf of the Panel to thank him for his hard work and commitment over the years and to wish him well in his retirement. | PCP Officers / Cllr Lowe | 2015-05-15 | COMPLETED
2015-04-24 | 9.8.1 | That the OPCC circulate the missing CJS performance appendix outside of the meeting | OPCC / PCP Officers | ASAP | COMPLETED
2014-11-07 | 6.4.1 | Victim Services – That the Commissioner brings a high-level evaluation report of the sixteen victim services projects in the new year. | PCC | 2015-06-12 | Report to Panel meeting on 24 April 2015. DEFERRED to 12 June 2015
2015-04-24 | 13.4.1 | That due to the poor response from Crime and Disorder Scrutiny Committees, Panel Members were asked to encourage participation from their respective authorities. | PCP Members | Ongoing | PCP Officers have sent out the latest Local Perspectives Survey and Members have been asked for their assistance in ensuring it is completed on time. Will report to the July Panel meeting.
2015-04-24 | 13.4.2 | Police and Crime Panel Officers to ensure Panel Members are aware when the Local Perspectives information is requested from their respective authorities. | PCP Officers | Ongoing | PCP Officers have sent out the latest Local Perspectives Survey and Members have been asked for their assistance in ensuring it is completed on time. Will report to the July Panel meeting.
2015-04-24 | 8.5.1 | That the Commissioner provides a report on the work of the WyFi team to a future meeting | PCC | 2015-07-17 | Included on agenda
2015-06-12 | 9.2.2 | That the Annual Report be sent to all elected Members across West Yorkshire as well as the Policing Minister, Keith Vaz (Home Affairs Select Committee), David Livesey (Home Office) and Mike Cunningham (HMIC). | PCP Officers | ASAP | COMPLETED
2015-01-15 | 1.4 | PCP Officers to work with the OPCC to look at potential venues for future Panel meetings with the possibility of the Chief Constable or District Commander attending with the PCC | PCP Officers/ OPCC | 2015-04-30 | PCP Officers to consider venues in Districts and liaise with KL before end April 15. KL to check MBW's diary for the September meeting. Venue confirmed as Dewsbury Town Hall. COMPLETED.
2014-04-11 | 8.10.2 | That the Commissioner considers how the Panel might provide help and support as he develops his plan to respond to points raised by the Crawford Review. | OPCC / PCP Officers | 2015-04-30 | Cllr Wassell has volunteered to work with the OPCC on the Crawford Review implementation plan. Julie Reid to contact the PCP Officers to arrange. Initial meeting has already taken place between Cllr Wassell, Julie Reid and PSD. KL to speak to JR re: Crawford Review implementation. PCP officers to work with the OPCC to develop new complaints process for Panel. Update paper on the Crawford review implementation to go to the June meeting.
2015-06-12 | 12.3.1 | PCP Officers to invite an LGA representative to the Panel’s Awayday | PCP Officers | 2015-06-25 | LGA rep has agreed to attend Panel Awayday 3 July 15. COMPLETED.
2015-06-12 | 17.6.3 | The Commissioner to circulate the letter regarding the Home Office Review of Police Targets and for the Panel to forward any views back to the OPCC | PCC | 2015-06-12 | Received from the OPCC on 12 June and sent out to Panel Members for their comments. JS asked that the OPCC provides the Panel with theirs and the Force response. OPCC to confirm with the PCC. OPCC response circulated to Members 8 July 15
2015-06-12 | 18.6.1 | That the Commissioner provides information to the Police and Crime Panel Officers on the reasons for the increase in blackmail | PCC | 2015-07-17
2014-11-07 | 8.5.1 | That the Commissioner invites Panel members to future Safer Communities funding award events | PCC | 2015-08-01 | Awards were cancelled due to snow. Alternative dates to be supplied by KL. First date is in August 2015, venues yet to be confirmed. First awards to be held on 6 August in Kirklees/Calderdale tbc. Members invited.
2015-07-17 | 13.3.2 | That the T/CC be invited to the Nov meeting to give an update on the SPR | PCC | 2015-07-29 | OPCC to invite T/CC Collins to Nov meeting | Completed
2015-07-17 | 5.9.3 | That the Commissioner circulate to the Panel for comment his proposed section on holding the Commissioner to account, as a matter of urgency | PCC | 2015-08-15 | Members should be allowed time to comment before publication of the Annual Report. Circulated to Members and response provided on 21 August 15. | Completed
2015-07-17 | 5.9.2 | That the Commissioner fully review the grammar and writing of the Annual Report before publication | PCC | 2015-08-31 |  | Completed
2015-07-17 | 5.9.4 | The Commissioner to review the data in the annual report to ensure it is as up to date as possible | PCC | 2015-08-31 |  | Completed
2015-07-17 | 8.8.3 | The Commissioner to forward his response to the HMIC inspection report on Child Protection | PCC | 2015-08-31 | Received from OPCC on 21 July and forwarded to Panel Members | Completed
2015-06-12 | 17.6.1 | The Commissioner to ask the Temporary Chief Constable to update Chief Officer Profiles on the Force website. | PCC | Ongoing | The website has been updated. | Completed
2015-07-17 | 8.8.2 | The Commissioner to forward information to the Panel on HMIC reporting on efficiency and effectiveness and to arrange discussion at a future meeting | PCC |  | Letter received by OPCC from HMIC about Force Management Statements and shared with Panel members July 2015. The changes aren’t due to be brought in until 2017 but happy to keep the Panel updated outside of meetings if any developments. | Completed
2015-07-17 | 6.3.1 | That the Commissioner provide further information regarding the staffing and work of the WyFi team in a much more user-friendly manner | PCC | 2015-08-31 | To be circulated prior to the meeting in Sept 15
2015-07-06 | 1:1 with AL and MBW | Commissioner has asked the Panel to consider reducing public meetings from 8 to 6, plus 2 additional private themed meetings | Panel Members | 2015-07-17 | Discussion at Panel meeting on 17 July. Decision made to maintain at 8. Dates for 2016 to be confirmed at meeting on 11 Sep 15.
2015-09-11 | 9.3.1 | Panel Officers to develop an outline of the scrutiny review of the Force’s treatment of vulnerable victims and vulnerable perpetrators. | PCP / OPCC | 2015-10-31 | To be discussed at Panel's private meeting on 9th Oct. ED to draft outline for OPCC to comment on prior to 9 Oct. Sent to OPCC on 21 Oct to finalise. | Completed
2015-04-24 | 14.2.1 | That Councillor Wassell (Wakefield), Councillor Scott (Kirklees), Councillor Walls (Bradford) and Councillor Barker (Wakefield) form a Complaints Sub Committee to specifically consider the complaint | PCP | 2015-10-31 | Await outcome from IPCC before proceeding. ED to advise. Appeal still with IPCC. ED contacted IPCC for a second time on 3 July. Awaiting response. IPCC have now referred complaint back to Panel 23 July 15. Complaints Sub Committee met on 21 August. Further information to be requested from the Commissioner prior to Complaints Sub Committee reconvening to discuss LR. | Completed
2015-09-11 | 6.9.1 | The Commissioner to provide information on the ANPR Transformation Project and the projected completion dates for installing ANPR cameras | PCC | 2015-11-13 | Requested by Cllr G Carter. Will also form part of the Transformation Update on 13 Nov 15. Panel members invited to ANPR Unit. | Completed
2015-09-11 | 11.4.1 | Panel Officers to circulate 2016 Panel meeting dates when confirmed | PCP | 2015-11-13 | Dates circulated. ED to confirm with PCP re: November date being changed at the meeting on 9th Oct | Completed
2015-09-11 | 12.7.2 | The Commissioner to provide the Force’s guidelines to staff on the use of social media | PCC | 2015-11-13 | Outside the formal meeting | Completed
2015-09-11 | 7 | The Commissioner to provide details of the number of BME officers by rank | PCC | 2015-11-13 |  | Completed
2015-06-12 | 9.2.3 | PCP to seek opportunities to launch the Annual Report to the media | PCP Officers | 2015-11-13 | ED to discuss with Cllrs Ahmed and Martin. | Completed
2015-09-11 | 13.4.1 | That the full Panel consider the appeal at its meeting on 13th November 15 | PCP | 2015-11-13 |  | Completed
2015-06-12 | 14.8.1 | The Commissioner to ensure that the Complaints Oversight (formely Crawford Review) implementation plan includes more detail and have clear timescales for each action | PCC | 2015-11-13 | The OPCC to incorporate the Panel's comments of the 12 June 15 and to report back to Nov or Dec meeting. | Completed
2015-09-11 | 8.8.1 | The Commissioner to provide a report on victims' hubs to a future meeting | PCC | 2015-11-13 | Verbal update provided on 13 Nov 15 | Completed
2015-11-13 | 14.2.1 | Make amendments to the Emergency Meetings Protocol as per the discussion | PCP | 2015-11-30 | PCP Officers to amend.
2015-07-17 | 13.3.1 | That the September meeting have a Prevent theme. Interested parties to be invited | PCP | 2015-12-11 | PCP Officers to discuss with OPCC. Prevent to be discussed at Dec 15 meeting (part of SPR report).
2015-11-13 | 8.3.1 | The Commissioner invited Members to visit one of the Victims' Hubs | PCP | 2016-03-31 | PCP Officer to provide details to Members.
2015-04-24 | 6.5.1 | That the Commissioner continues to look at opportunities for joint commissioning where possible | PCC | Ongoing | KL to speak to Trish Holder for an update (24/9/15). Currently awaiting the CSR annoucement to finalise future plans and look at joint commissioing opportunities. Partner Transformation Event being held by the PCC early December. Invite has been sent to Chair of the PCP.
2015-09-11 | 6.9.2 | The Commissioner agreed to include homicide figures in the next quarterly performance report | PCC | 2015-12-11 | Requested by Roger Grasby.
2015-11-13 | 13.3.1 | A new Complaints Sub Panel to be formed to consider new complaints | PCP | 2016-01-14 | Meeting arranged for 9 December. Information requested from complainant and PCC. 2nd meeting arranged in Jan 16.
2015-09-11 | 12.7.1 | The Commissioner to provide further information on West Yorkshire Police’s approach to the seizure and sale of cars | PCC | 2015-12-11 | Outside the formal meeting. Information to be provided ahead of the meeting. KL has spoken to the Force. Aiming to provide it before December meeting.
2015-11-13 | 10.2.1 | The Commissioner was asked to provide full Panel with information on the full costs to West Yorkshire of the redeployment of Mark Gilmore. | PCC | 2015-12-11 | Update to be provided at the Dec meeting.
2015-09-11 | 7.8.1 | The Commissioner to provide a briefing to Members on the Strategic Workforce Plan, potentially at their private meeting on 9 October 2015 | PCC | 2016-01-22 | Agreed at 1:1 on 2 Dec 15 that this would be provided to the private meeting of the Panel in January.
2015-11-13 | 12.4.1 | Panel to consider the full PEEL report at a future meeting | PCC | 2016-03-11 | When all PEEL inspection reports are available.
2015-11-13 | 9.3.2 | That the Commissioner provides updates and involves Panel members in discussions about changes to overseeing the Police Complaints system. | PCC/PCP | Ongoing
2015-12-11 | 5.6.1 | That the Panel share details of Force recruitment with community groups to encourage applicants from diverse backgrounds | PCP
2015-06-12 | 17.6.2 | The Commissioner to keep the Panel informed of any progress on the Armed Forces Covenant | PCC | Ongoing | Dialogue is ongoing between the OPCC and WYP (04/11)
2015-09-11 | 5.9.2 | The Commissioner to provide details of police officers on restricted duties and how they are being utilised across the Force | PCC | 2016-03-11 | Requested by Roger Grasby. Information provided outside of formal meeting structure. More detailed report required for public meeting (13 Nov 15)
2015-07-17 | 8.8.1 | The Commissioner to look at the progression of co-location with the Fire and Rescue Service at Weetwood Police Station and respond to the Panel outside the meeting process | PCC | 2015-12-11 | Information to be provided ahead of the meeting on 11 Sep 15. Brief update provided on 11 Sep. Ongoing issue. Changes have been made to the original proposal from Leeds CC and WYFRS and alternative options are being explored by both (26/02)
2016-02-06 | 7.2 | Cllr G Carter to attend the LGA's Panel conference on 14 March with Sam | Panel | 2016-03-14 | SW / ED to try and secure more places for Cllr Ahmed and Mrs Sykes to attend. Places secured for 4 people to attend. SW / ED to arrange train tickets for Members.
2016-03-11 | 7.5.1 | OPCC to re-issue the performance report appendices due to an error being highlighted | PCC | 2016-03-31 | ED emailed LW on 31 March for the amended report. Sent to members 31/3/16
2016-03-11 | 13.3.2 | That an additional meeting of the full Police and Crime Panel be convened on 6 April to consider a complaint appeal | Panel | 2016-04-06
2016-03-11 | 12.2.1 | That the reference to senior staff in part 7 of the Panel's Arrangements and Rules of Conduct be removed and replaced with Deputy PCC | Panel | 2016-03-31
2016-03-11 | 13.3.1 | A new Complaints Sub Panel to be arranged to consider the newly recorded complaint. | Panel | 2016-04-30 | Meeting arranged on 26 April 16
2016-03-11 | 11.5.1 | The PCC to share his response to HMIC's report on Child Protection Post-Inspection Review report | PCC | 2016-04-22
2016-04-22 | 9.2.1 | That the PCC shares his response to HMIC's report on WYP's Child Protection Inspection | PCC | 2016-04-22 | Emailed to Panel Members on 22 April 16.
2016-04-22 | 10.12.1 | That arrangements are made for Mr Lake to meet with the Scrutiny Review Team to discuss commissioning of services. | PCP | 2016-06-10 | ED/SW to contract Trevor Lake to arrange.
2015-11-13 | 2.4.3 | The Commissioner agreed to look at the College of Policing's Equality and Diversity initiative and see what learning there might be for West Yorkshire. | PCC | 2016-01-31 | Clarity on the specific initiative is required and email sent to SW/ED to liaise with JS (17/02)
2016-06-10 | 9.1.1 | Complaints Procedures - officers to make final amendments | PCP | 2016-07-15
2016-06-10 | 17.1.5 | The Commissioner provides detail on the number of successful BME applicants overall and female BME applicants to police officers | PCC | 2016-07-15 | To be included in the recruitment report.
2016-06-10 | 17.4.3 | The Commissioner to provide the response from WYP on the IPCC report into Sussex | PCC | 2016-07-15 | Kelly requested from WYP - awaiting response.
2016-06-10 | 18.1.3 | Panel to write to Mike Penning MP in support of the proposal to change the names of PCPs to include Fire where appropriate | PCP | 2016-06-17 | Letter sent on 14 June 16
2016-06-10 | 19.4 | Inform the complainant of the outcome of the review of the Complaints Sub Panel's decision | PCP | 2016-06-17 | Letter sent on 14 June 16
2016-07-15 | 15.1 | Panel officers to draft a response to PCC's partnership consultation survey and circulate to members for approval prior to submission | Panel | 2016-08-01
2016-07-15 | 5.7.3 | ACC Battle to check whether data on arrests that were directly attributable to ANPR is available prior to the introduction of the enhanced ANPR system | PCC | 2016-09-09 | There were 51 arrests attributable to ANPR in the previous year and this will be used as a baseline to measure the effectiveness of the enhanced ANPR system.
2016-07-15 | 6.5.1 | The PCC to provide detail of how he is holding the Force to account for the 5/6% 'real' increase in recorded crime | PCC | 2016-09-09 | To be included in the Quarterly Performance report.
2016-07-15 | 11.2.1 | Cllrs Lowe, Wassell and Wilkinson to form a sub panel to recruit independent members | PCP | 2016-11-04 | Outline timetable to be brought forward by one week. Shortlisting - 10am on 26 Sep 16 Interviews - 1pm on 6 Oct 16 Panel officers to arrange rooms. Rooms arranged.
2016-09-09 | 14.4 | That Panel Members contact Panel Officers if they wish to attend the Panel Conference on 20 October 16 | PCP |  | Alan, Josie and Sam to attend
2016-09-09 | 14.3 | That the Panel's Annual Report be disseminated widely | PCP |  | Panel officers to distribute asap
2016-09-09 | 5.11.1 | Panel to provide a report to the PCC following the Interim Chief Executive confirmation hearing | PCP | 2016-10-14 | Panel Officers sent the report to the PCC on 12 Oct 16 and published it on the Panel's website |  | Completed
2016-10-07 | 6.7.1 | That Members provide feedback to Officers on the draft Police and Crime Plan | PCP | 2016-10-14 | Roger and Steve to meet with the OPCC on 19 October to discuss. Feedback provided to the OPCC. Panel to receive a revised Plan by 26 Oct 16. |  | Completed
2016-10-07 | 6.7.3 | Revised draft Police and Crime Plan to Panel before 4 November meeting | PCC | 2016-11-04 | Deadline 26 Oct 16 |  | Completed
2016-10-07 | 6.7.4 | PCC to provide the Needs Assessment surrounding the Police and Crime Plan | PCC | 2016-11-04 | Deadline 26 Oct 16 |  | Completed
2016-10-07 | 7.4.2 | Panel's Monitoring Officer to consider formalising the appointment of the 2 co-opted independent members | PCP | 2016-11-30 | Sam to discuss with Bernadette. |  | Completed
|  | That the PCC keeps the Panel informed re: recruitment of new Chief Constable | PCC | 2016-11-11 | Recruitment timetable sent to Panel Officers. Confirmation hearing to be held on 11 Nov 16. |  | Completed
2016-09-09 | 12b.5 | Panel to provide a report to the PCC following the Interim Chief Executive confirmation hearing | PCP | 2016-10-14 | Panel Officers sent the report to the PCC on 12 Oct 16 and published it on the Panel's website |  | Completed
2016-09-09 | 5.11.1 | That Members provide feedback to Officers on the draft Police and Crime Plan | PCP | 2016-10-14 | Roger and Steve to meet with the OPCC on 19 October to discuss. Feedback provided to the OPCC. Panel to receive a revised Plan by 26 Oct 16. |  | Completed
2016-10-07 | 6.7.1 | Revised draft Police and Crime Plan to Panel before 4 November meeting | PCC | 2016-11-04 | Deadline 26 Oct 16 |  | Completed
2016-10-07 | 6.7.3 | PCC to provide the Needs Assessment surrounding the Police and Crime Plan | PCC | 2016-11-04 | Deadline 26 Oct 16 |  | Completed
2016-10-07 | 6.7.4 | Panel's Monitoring Officer to consider formalising the appointment of the 2 co-opted independent members | PCP | 2016-11-30 | Sam to discuss with Bernadette. |  | Completed